## Summary Sheet - All Projects
Summary of Apple Capital Loop Network of Projects
Minimum Timeline Requirements
|  | Schedule based on contract date of (obligation): | 2022-11-01
|  | Construction Must Start before (+ 18 Months) | 2024-04-24
|  | Match Starts Counting on | 2020-09-30 | Match counts at project award
Legend
Project Totals
Eligible Future Costs and Sources
Pre-Match Invested
PE and ROW
|  | Construction | [5 empty] | <= Pre-Match | Match =>
Funding Sources
|  | Source | Eligible Future | Total Project | Total Previous Invested | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | Total By Source
Local
|  | City of Wenatchee | 11000000 | 15134981.0648 | 274092.4489 | 479309.265 | 494034.9094 | 847492.2514 | 2040052.19 | 3500000 | 7500000 | 0 | 0 | 0 | 0 | 0 | 14860888.6158
|  | Douglas Co./Port of Douglas Co. | 0 | 264082 | 264082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Chelan - Douglas Transportation Council | 0 | 570000 | 570000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Link | 0 | 400000 | 0 | 0 | 0 | 250000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
|  | BNSF | 1000000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 1000000
|  | Other | 1500000 | 3059000 | 0 | 859000 | 93899 | 106101 | 500000 | 500000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 3059000
0
| Local Subtotal |  | 13500000 | 20428063.0648 | 1108174.4489 | 1338309.265 | 587933.9094 | 1203593.2514 | 2690052.19 | 4000000 | 8500000 | 0 | 1000000 | 0 | 0 | 0 | 19319888.6159
State | [16 empty] | 0
|  | Transit Grant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FMSIB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | State of Washington - Requested | 31924200 | 31924200 | 0 | 0 | 0 | 0 | 0 | 0 | 546000 | 10400000 | 20978200 | 0 | 0 | 0
|  | Connecting Washington Sunset Highway | 55857089 | 58522010 | 19794 | 3243 | 308122 | 2333762 | 6083766 | 9333764 | 6333764 | 7705795 | 11400000 | 10000000 | 5000000 | 0 | 58502216
|  | Connecting Washington North Wenatchee Avenue | 21140693 | 23000001 | 0 | 163576 | 171700 | 667099 | 856933 | 896216 | 7543950 | 7510817 | 3732152 | 1084884 | 372674 | 0 | 23000001
|  | CERB - Dept. of Commerce | 0 | 138000 | 25000 | 113000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113000
|  | Transportation Improvement Board | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | State of Washington - Other | 0 | 8613296 | 7600000 | 139257 | 874039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1013296
0
| State Subtotal |  | 108921982 | 122197507 | 7644794 | 419076 | 1353861 | 3000861 | 6940699 | 10229980 | 14423714 | 25616612 | 36110352 | 11084884 | 5372674 | 0 | 114552713
Federal | [16 empty] | 0
|  | STP | 0 | 3225386.7853 | 171112.6911 | 63178.735 | 657867.1605 | 1115486.3886 | 1217741.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3054274.0942
|  | INFRA | 140414116 | 140414116 | 0 | 0 | 0 | 0 | 0 | 3019502 | 16889616 | 32060322 | 48916969 | 34954707 | 4573000 | 0 | 140414116
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| Federal Subtotal |  | 140414116 | 143639502.7853 | 171112.6911 | 63178.735 | 657867.1605 | 1115486.3886 | 1217741.81 | 3019502 | 16889616 | 32060322 | 48916969 | 34954707 | 4573000 | 0 | 143468390.0942
0
Funding Source Grant Total |  |  | 262836098 | 286265072.85 | 8924081.14 | 1820564 | 2599662.07 | 5319940.64 | 10848493 | 17249482 | 39813330 | 57676934 | 86027321 | 46039591 | 9945674 | 0 | 277340991.71
Project Costs
|  | Sub-project | Future Eligible | Total Project | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | Total By Phase 2018-2027
0
#1 North Wenatchee |  |  | 52664893 | 61743497.85 | 420205.14 | 1678064 | 1129430.07 | 2086178.64 | 3764727 | 2396216 | 13089950 | 22510817 | 13210352 | 1084884 | 372674 | 0 | 61323292.71
0
| 1A - North Wenatchee Avenue |  | 16793597 | 18236277 | 42387 | 355025 | 171110 | 390140 | 484018 | 847816 | 4247499 | 6508572 | 3732152 | 1084884 | 372674 | 0 | 18236277
|  | Preliminary Engineering | 1508008 | 2702352 | 42387 | 355025 | 171110 | 342938 | 282884 | 492149 | 980426 | 35433 | 0 | 0 | 0 | 0 | 2659965
|  | Environmental-Permitting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Right of Way | 1346664 | 1475000 | 0 | 0 | 0 | 47202 | 81134 | 43997 | 486000 | 816667 | 0 | 0 | 0 | 0 | 1475000
|  | Construction Engineering | 2090838.75 | 2108838.75 | 0 | 0 | 0 | 0 | 18000 | 46750.5 | 417160.95 | 848470.8 | 559822.8 | 162732.6 | 55901.1 | 0 | 2108838.75
|  | Construction | 10454193.75 | 10544193.75 | 0 | 0 | 0 | 0 | 90000 | 233752.5 | 2085804.75 | 4242354 | 2799114 | 813663 | 279505.5 | 0 | 10544193.75
|  | Contingency | 1393892.5 | 1405892.5 | 0 | 0 | 0 | 0 | 12000 | 31167 | 278107.3 | 565647.2 | 373215.2 | 108488.4 | 37267.4 | 0 | 1405892.5
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| 1B - McKittrick RR Underpass & McK./Wen. Signal |  | 31524200 | 38507219.85 | 377818.14 | 1323039 | 955289.07 | 1419079.64 | 2907794 | 1500000 | 5546000 | 15000000 | 9478200 | 0 | 0 | 0 | 38129401.71
|  | Preliminary Engineering | 2046000 | 4330885.85 | 328987.31 | 26369.33 | 276839.21 | 152690 | 1500000 | 1500000 | 546000 | 0 | 0 | 0 | 0 | 0 | 4001898.54
|  | Environmental-Permitting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Right of Way | 0 | 3290340 | 48830.83 | 1296669.67 | 678449.86 | 1266389.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3241509.17
|  | Construction Engineering | 2837000 | 2837000 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000 | 837000 | 0 | 0 | 0 | 2837000
|  | Construction | 23639000 | 25046794 | 0 | 0 | 0 | 0 | 1407794 | 0 | 3000000 | 13000000 | 7639000 | 0 | 0 | 0 | 25046794
|  | Contingency | 3002200 | 3002200 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000 | 1002200 | 0 | 0 | 0 | 3002200
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| 1C - US2 Roundabout |  | 4347096 | 5000001 | 0 | 0 | 3031 | 276959 | 372915 | 48400 | 3296451 | 1002245 | 0 | 0 | 0 | 0 | 5000001
|  | Preliminary Engineering | 6021 | 633926 | 0 | 0 | 3031 | 276959 | 347915 | 6021 | 0 | 0 | 0 | 0 | 0 | 0 | 633926
|  | Environmental-Permitting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Right of Way | 0 | 25000 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
|  | Construction Engineering | 651161.25 | 651161.25 | 0 | 0 | 0 | 0 | 0 | 6356.85 | 494467.65 | 150336.75 | 0 | 0 | 0 | 0 | 651161.25
|  | Construction | 3255806.25 | 3255806.25 | 0 | 0 | 0 | 0 | 0 | 31784.25 | 2472338.25 | 751683.75 | 0 | 0 | 0 | 0 | 3255806.25
|  | Contingency | 434107.5 | 434107.5 | 0 | 0 | 0 | 0 | 0 | 4237.9 | 329645.1 | 100224.5 | 0 | 0 | 0 | 0 | 434107.5
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
0
#2 Confluence Parkway |  |  | 137949360 | 141157431 | 620000 | 0 | 688071 | 900000 | 1000000 | 4777901 | 19789400 | 20154056 | 56400000 | 32255003 | 4573000 | 0 | 140537431
0
| 2A - Confluence Pkwy Phase 1 (Hawley St - S.) |  | 61087756 | 61837756 | 0 | 0 | 50000 | 200000 | 500000 | 2250000 | 6000000 | 6388428 | 31000000 | 15449328 | 0 | 0 | 61837756
|  | Preliminary Engineering | 4350000 | 5000000 | 0 | 0 | 50000 | 100000 | 500000 | 1850000 | 2500000 | 0 | 0 | 0 | 0 | 0 | 5000000
|  | Environmental-Permitting | 0 | 500000 | 0 | 0 | 0 | 100000 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000
|  | Right of Way | 9648428 | 9648428 | 0 | 0 | 0 | 0 | 0 | 0 | 6148428 | 0 | 0 | 0 | 0 | 0 | 6148428
|  | Construction Engineering | 4400000 | 4400000 | 0 | 0 | 0 | 0 | 0 | 0 | 240000 | 3000000 | 1160000 | 0 | 0 | 0 | 4400000
|  | Construction | 36669000 | 36669000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000000 | 11669000 | 0 | 0 | 0 | 36669000
|  | Contingency | 5620328 | 5620328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 2620328 | 0 | 0 | 0 | 5620328
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| 2B - Confluence Pkwy Phase 2 (Hawley St - N.) |  | 66861604 | 69269675 | 570000 | 0 | 638071 | 700000 | 500000 | 1727901 | 9189400 | 9165628 | 25400000 | 16805675 | 4573000 | 0 | 68699675
|  | Preliminary Engineering | 4699578 | 5711000 | 320000 | 0 | 208762 | 200000 | 282660 | 1000000 | 3699578 | 0 | 0 | 0 | 0 | 0 | 5391000
|  | Environmental-Permitting | 1053351 | 2450000 | 250000 | 0 | 429309 | 500000 | 217340 | 727901 | 325450 | 0 | 0 | 0 | 0 | 0 | 2200000
|  | Right of Way | 9970000 | 9970000 | 0 | 0 | 0 | 0 | 0 | 5164372 | 4805628 | 0 | 0 | 0 | 0 | 0 | 9970000
|  | Construction Engineering | 4312700 | 4312700 | 0 | 0 | 0 | 0 | 0 | 0 | 360000 | 2400000 | 1200000 | 352700 | 0 | 0 | 4312700
|  | Construction | 35939000 | 35939000 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 20000000 | 10000000 | 2939000 | 0 | 0 | 35939000
|  | Contingency | 10886975 | 10886975 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 3000000 | 5605675 | 1281300 | 0 | 0 | 10886975
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| 2C - South End Bike/ Ped Access Bridge |  | 10000000 | 10050000 | 50000 | 0 | 0 | 0 | 0 | 800000 | 4600000 | 4600000 | 0 | 0 | 0 | 0 | 10000000
|  | Preliminary Engineering | 600000 | 650000 | 50000 | 0 | 0 | 0 | 0 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 600000
|  | Environmental-Permitting | 200000 | 200000 | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
|  | Right of Way | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Construction Engineering | 1040000 | 1040000 | 0 | 0 | 0 | 0 | 0 | 0 | 520000 | 520000 | 0 | 0 | 0 | 0 | 1040000
|  | Construction | 5400000 | 5400000 | 0 | 0 | 0 | 0 | 0 | 0 | 2700000 | 2700000 | 0 | 0 | 0 | 0 | 5400000
|  | Contingency 10% | 2760000 | 2760000 | 0 | 0 | 0 | 0 | 0 | 0 | 1380000 | 1380000 | 0 | 0 | 0 | 0 | 2760000
0
#3 Cascade Interchange |  |  | 16364756 | 17242134 | 264082 | 139257 | 474039 | 0 | 0 | 741601 | 600216 | 7306266 | 5016969 | 2699704 | 0 | 0 | 16978052
0
| 3A - Hwy Iterchange |  | 16364756 | 16628838 | 264082 | 0 | 0 | 0 | 0 | 741601 | 600216 | 7306266 | 5016969 | 2699704 | 0 | 0 | 16364756
|  | Preliminary Engineering | 1072179 | 1336261 | 264082 | 0 | 0 | 0 | 0 | 635658 | 436521 | 0 | 0 | 0 | 0 | 0 | 1072179
|  | Environmental-Permitting | 269638 | 269638 | 0 | 0 | 0 | 0 | 0 | 105943 | 163695 | 0 | 0 | 0 | 0 | 0 | 269638
|  | Right of Way | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Construction Engineering | 1421912 | 1421912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 843031 | 578881 | 0 | 0 | 0 | 1421912
|  | Construction | 12179115 | 12179115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5620204 | 3859207 | 2699704 | 0 | 0 | 12179115
|  | Contingency | 1421912 | 1421912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 843031 | 578881 | 0 | 0 | 0 | 1421912
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| 3B - | US2 /SR 28 Roundabouts (35th and 38th) | 0 | 613296 | 0 | 139257 | 474039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 613296
|  | Preliminary Engineering | 0 | 502992 | 0 | 139257 | 363735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 502992
|  | Environmental-Permitting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Right of Way | 0 | 110304 | 0 | 0 | 110304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110304
|  | Construction Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Contingency | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
#4 Sunset Highway/ SR28 Widening |  |  | 55857089 | 66122010 | 7619794 | 3243 | 308122 | 2333762 | 6083766 | 9333764 | 6333764 | 7705795 | 11400000 | 10000000 | 5000000 | 0 | 58502216
|  | Preliminary Engineering | 6357087 | 8722010 | 219794 | 3243 | 308122 | 1833764 | 1833764 | 1833764 | 1833764 | 855795 | 0 | 0 | 0 | 0 | 8502216
|  | Environmental-Permitting | 0 | 6000000 | 6000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Right of Way | 18500002 | 19000000 | 0 | 0 | 0 | 499998 | 4250002 | 7500000 | 4500000 | 1500000 | 750000 | 0 | 0 | 0 | 19000000
|  | Construction Engineering | 4650000 | 4650000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 802500 | 1597500 | 1500000 | 750000 | 0 | 4650000
|  | Construction | 23250000 | 24650000 | 1400000 | 0 | 0 | 0 | 0 | 0 | 0 | 4012500 | 7987500 | 7500000 | 3750000 | 0 | 23250000
|  | Contingency | 3100000 | 3100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 535000 | 1065000 | 1000000 | 500000 | 0 | 3100000
0
Cost Grand Total |  |  | 262836098 | 286265072.85 | 8924081.14 | 1820564 | 2599662.07 | 5319940.64 | 10848493 | 17249482 | 39813330 | 57676934 | 86027321 | 46039591 | 9945674 | 0 | 277340991.71
Net Surplus (Defecit) |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Match Summary
|  | Total Project Cost | 286265072.85
|  | Total Eligible Future Project Cost | 262836098 | 23428974.85
|  | Total INFRA Request | 140414116
|  | Total Eligible Future Non-Fed Match | 122421982
|  | Total Eligible Future Fed Match | 0
|  | Total Eligible Future Match | 122421982
|  | Percentage Match | 46.58%
|  | ROW | 39465094

## Summary by Phase
Summary of Apple Capital Loop Network of Projects
Legend
Project Totals
Eligible Future Costs and Sources
Pre-Match Invested
PE and ROW
|  | Construction | [6 empty] | <= Pre-Match | Match =>
Funding Sources
|  | Source | Eligible Future | Total Project | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | Total By Source
Local
|  | City of Wenatchee | 11000000 | 15134981.0648 | 274092.4489 | 479309.265 | 494034.9094 | 847492.2514 | 2040052.19 | 3500000 | 7500000 | 0 | 0 | 0 | 0 | 0 | 14860888.6158
|  | Douglas Co./Port of Douglas Co. | 0 | 264082 | 264082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Chelan - Douglas Transportation Council | 0 | 570000 | 570000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Link | 0 | 400000 | 0 | 0 | 0 | 250000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
|  | BNSF | 1000000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 1000000
|  | Other | 1500000 |  | 0 | 859000 | 93899 | 106101 | 500000 | 500000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 3059000
0
| Local Subtotal |  | 13500000 | 17369063.0648 | 1108174.4489 | 1338309.265 | 587933.9094 | 1203593.2514 | 2690052.19 | 4000000 | 8500000 | 0 | 1000000 | 0 | 0 | 0 | 19319888.6159
State | [16 empty] | 0
|  | Transit Grant | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FMSIB | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | State of Washington - Requested | 31924200 | 31924200 | 0 | 0 | 0 | 0 | 0 | 0 | 546000 | 10400000 | 20978200 | 0 | 0 | 0 | 31924200
|  | Connecting Washington Sunset Highway | 55857089 | 58522010 | 19794 | 3243 | 308122 | 2333762 | 6083766 | 9333764 | 6333764 | 7705795 | 11400000 | 10000000 | 5000000 | 0 | 58502216
|  | Connecting Washington North Wenatchee Avenue | 21140693 | 23000001 | 0 | 163576 | 171700 | 667099 | 856933 | 896216 | 7543950 | 7510817 | 3732152 | 1084884 | 372674 | 0 | 23000001
|  | CERB - Dept. of Commerce | 0 | 138000 | 25000 | 113000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113000
|  | Transportation Improvement Board | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | State of Washington - Other | 0 | 8613296 | 7600000 | 139257 | 874039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1013296
0
| State Subtotal |  | 108921982 | 122197507 | 7644794 | 419076 | 1353861 | 3000861 | 6940699 | 10229980 | 14423714 | 25616612 | 36110352 | 11084884 | 5372674 | 0 | 114552713
Federal | [16 empty] | 0
|  | STP | 0 | 3225386.7853 | 171112.6911 | 63178.735 | 657867.1605 | 1115486.3886 | 1217741.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3054274.0942
|  | INFRA | 140414116 | 140414116 | 0 | 0 | 0 | 0 | 0 | 3019502 | 16889616 | 32060322 | 48916969 | 34954707 | 4573000 | 0 | 140414116
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| Federal Subtotal |  | 140414116 | 143639502.7853 | 171112.6911 | 63178.735 | 657867.1605 | 1115486.3886 | 1217741.81 | 3019502 | 16889616 | 32060322 | 48916969 | 34954707 | 4573000 | 0 | 143468390.0942
0
Funding Source Grant Total |  |  | 262836098 | 283206072.85 | 8924081.14 | 1820564 | 2599662.07 | 5319940.64 | 10848493 | 17249482 | 39813330 | 57676934 | 86027321 | 46039591 | 9945674 | 0 | 277340991.71
Project Costs
|  | Sub-project | Future Eligible | Total Project | Previous Costs | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | Total By Phase
0
#1 North Wenatchee |  |  | 52664893 | 61743497.85 | 420205.14 | 1651694.67 | 1129430.07 | 2086178.64 | 3764727 | 2396216 | 13089950 | 22510817 | 13210352 | 1084884 | 372674 | 0 | 61296923.38
0
|  | Preliminary Engineering/Env. | 3560029 | 7667163.85 | 371374.31 | 355025 | 450980.21 | 772587 | 2130799 | 1998170 | 1526426 | 35433 | 0 | 0 | 0 | 0 | 7269420.21
|  | Right of Way | 1346664 | 4790340 | 48830.83 | 1296669.67 | 678449.86 | 1313591.64 | 106134 | 43997 | 486000 | 816667 | 0 | 0 | 0 | 0 | 4741509.17
|  | Construction Incl. Contingency | 47758200 | 49285994 | 0 | 0 | 0 | 0 | 1527794 | 354049 | 11077524 | 21658717 | 13210352 | 1084884 | 372674 | 0 | 49285994
0
#2 Confluence Parkway |  |  | 137549360 | 141157431 | 620000 | 0 | 688071 | 900000 | 1400000 | 9542273 | 26679084 | 61000000 | 32255003 | 4573000 | 0 | 0 | 137037431
0
|  | Preliminary Engineering/Env. | 10902929 | 14511000 | 620000 | 0 | 688071 | 900000 | 1400000 | 4377901 | 6525028 | 0 | 0 | 0 | 0 | 0 | 13891000
|  | Right of Way | 19618428 | 19618428 | 0 | 0 | 0 | 0 | 0 | 5164372 | 10954056 | 0 | 0 | 0 | 0 | 0 | 16118428
|  | Construction Incl. Contingency | 107028003 | 107028003 | 0 | 0 | 0 | 0 | 0 | 0 | 9200000 | 61000000 | 32255003 | 4573000 | 0 | 0 | 107028003
0
#3 Cascade Interchange |  |  | 16364756 | 17242134 | 264082 | 139257 | 474039 | 0 | 0 | 741601 | 600216 | 7306266 | 5016969 | 2699704 | 0 | 0 | 16978052
0
|  | Preliminary Engineering/Env. | 1341817 | 2108891 | 264082 | 139257 | 363735 | 0 | 0 | 741601 | 600216 | 0 | 0 | 0 | 0 | 0 | 1844809
|  | Right of Way | 0 | 110304 | 0 | 0 | 110304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110304
|  | Construction Incl. Contingency | 15022939 | 15022939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7306266 | 5016969 | 2699704 | 0 | 0 | 15022939
0
#4 Sunset Highway |  |  | 55857089 | 66122010 | 7619794 | 3243 | 308122 | 2333762 | 6083766 | 9333764 | 6333764 | 7705795 | 11400000 | 10000000 | 5000000 | 0 | 58502216
0
|  | Preliminary Engineering/Env. | 6357087 | 14722010 | 6219794 | 3243 | 308122 | 1833764 | 1833764 | 1833764 | 1833764 | 855795 | 0 | 0 | 0 | 0 | 8502216
|  | Right of Way | 18500002 | 19000000 | 0 | 0 | 0 | 499998 | 4250002 | 7500000 | 4500000 | 1500000 | 750000 | 0 | 0 | 0 | 19000000
|  | Construction Incl. Contingency | 31000000 | 32400000 | 1400000 | 0 | 0 | 0 | 0 | 0 | 0 | 5350000 | 10650000 | 10000000 | 5000000 | 0 | 31000000
0
0
Apple Capital Loop Network of Project by Phase |  |  | 262436098 | 286265072.85 | 8924081.14 | 1794194.67 | 2599662.07 | 5319940.64 | 11248493 | 22013854 | 46703014 | 98522878 | 61882324 | 18357588 | 5372674 | 0 | 273814622.38
0
|  | Preliminary Engineering/Env. | 22161862 | 39009064.85 | 7475250.31 | 497525 | 1810908.21 | 3506351 | 5364563 | 8951436 | 10485434 | 891228 | 0 | 0 | 0 |  | 31507445.21
|  | Right of Way | 39465094 | 43519072 | 48830.83 | 1296669.67 | 788753.86 | 1813589.64 | 4356136 | 12708369 | 15940056 | 2316667 | 750000 | 0 | 0 |  | 39970241.17
|  | Construction Incl. Contingency | 200809142 | 203736936 | 1400000 | 0 | 0 | 0 | 1527794 | 354049 | 20277524 | 95314983 | 61132324 | 18357588 | 5372674 |  | 202336936
0
Cost Grand Total |  |  | 262436098 | 286265072.85 | 8924081.14 | 1794194.67 | 2599662.07 | 5319940.64 | 11248493 | 22013854 | 46703014 | 98522878 | 61882324 | 18357588 | 5372674 | 0 | 273814622.38
Net Surplus (Defecit) |  |  | 400000 |  | 0 | 26369.33 | 0 | 0 | -400000 | -4764372 | -6889684 | -40845944 | 24144997 | 27682003 | 4573000 | 0 | 3526369.33
|  | Total Project Contingency | 28619415 | Added Contingency om top of engineer's cost estimate
172189727
|  | Preliminary Engineering/Env. | 22161862 | 8.445%
|  | Right of Way | 39465094 | 15.04%
|  | Construction | 172189727 | 65.61%
|  | Contingency | 28619415 | 10.91% | Added Contingency in addition to contingency in construction est.
|  | Aditional Contingency as Percentage of Construction | 16.62%
|  | Project Cost Components | Cost (in millions) | Percent
|  | Preliminary Engineering | 22.2 | 8.4%
|  | Right of Way | 39.5 | 15%
|  | Construction (Incl. Const. Engineering and 15% contingency on Eng. Est.) | 172.2 | 65.6%
|  | Additional Contingency1 | 28.9 | 10.9%
|  | Total Project Cost | 262.8 | 100%
1 Additional Contingency added onto Construction Estimate. Total Contingency averages 25-30% of Construction costs

## Schedule
Schedule for the Apple Capital Loop Network of Projects
Minimum Timeline Requirements
|  | Schedule based on contract date (obligation): | 2022-11-01
|  | Construction Must Start before (+ 18 Months) | 2024-04-24
|  | Match Starts Counting on | 2020-09-30 | Match counts at project award
Legend
Project Totals
Eligible Future Costs and Sources
Pre-Match Invested
PE and ROW
Construction
[8 empty] | <= Pre-Match | Match =>
Funding Sources
|  | Source | Eligible Future | Total Project | Total Previous Invested | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | Total By Source
Local
|  | City of Wenatchee | 11000000 | 15134981.0648 | 274092.4489 | 479309.265 | 494034.9094 | 847492.2514 | 2040052.19 | 3500000 | 7500000 | 0 | 0 | 0 | 0 | 0 | 15134981.0648
|  | Douglas County | 0 |  | 264082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Chelan - Douglas Transportation Council | 0 |  | 570000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Link | 0 |  | 0 | 0 | 0 | 250000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400000
|  | BNSF | 1000000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 1000000
|  | Other | 1500000 |  | 0 | 859000 | 93899 | 106101 | 500000 | 500000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 3059000
0
| Local Subtotal |  | 13500000 | 16134981.0648 | 274092.4489 | 479309.265 | 494034.9094 | 847492.2514 | 2040052.19 | 3500000 | 7500000 | 0 | 1000000 | 0 | 0 | 0 | 16134981.0648
State | [16 empty] | 0
|  | Transit Grant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FMSIB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | State of Wasington - Other | 31924200 | 31924200 | 0 | 0 | 0 | 0 | 0 | 0 | 546000 | 10400000 | 20978200 | 0 | 0 | 0 | 31924200
|  | Connecting Washington Sunset Highway | 55857089 | 58522010 | 19794 | 3243 | 308122 | 2333762 | 6083766 | 9333764 | 6333764 | 7705795 | 11400000 | 10000000 | 5000000 | 0 | 58522010
|  | Connecting Washington North Wenatchee Ave | 21140693 | 23000001 | 0 | 163576 | 171700 | 667099 | 856933 | 896216 | 7543950 | 7510817 | 3732152 | 1084884 | 372674 | 0 | 23000001
|  | CERB - Dept. of Commerce | 0 | 138000 | 25000 | 113000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113000
|  | Transportation Improvement Board | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | State of Wasington - Other | 0 | 8613296 | 7600000 | 139257 | 874039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8613296
0
| State Subtotal |  | 108921982 | 122197507 | 7644794 | 419076 | 1353861 | 3000861 | 6940699 | 10229980 | 14423714 | 25616612 | 36110352 | 11084884 | 5372674 | 0 | 122197507
Federal | [16 empty] | 0
|  | STP | 0 | 3225386.7853 | 171112.6911 | 63178.735 | 657867.1605 | 1115486.3886 | 1217741.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3225386.7853
|  | INFRA | 140414116 | 140414116 | 0 | 0 | 0 | 0 | 0 | 3019502 | 16889616 | 32060322 | 48916969 | 34954707 | 4573000 | 0 | 140414116
|  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| Federal Subtotal |  | 140414116 | 143639502.7853 | 171112.6911 | 63178.735 | 657867.1605 | 1115486.3886 | 1217741.81 | 3019502 | 16889616 | 32060322 | 48916969 | 34954707 | 4573000 | 0 | 143639502.7853
0
Funding Source Grant Total |  |  | 262836098 | 281971990.85 | 8089999.14 | 961564 | 2505763.07 | 4963839.64 | 10198493 | 16749482 | 38813330 | 57676934 | 86027321 | 46039591 | 9945674 | 0 | 273881991.71
Project Costs
|  | Sub-project | Future Eligible | Total Project | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | Total By Phase
0
#1 North Wenatchee |  |  | 52664893 | 61743497.85 | 420205.14 | 1678064 | 1129430.07 | 2086178.64 | 3764727 | 2396216 | 13089950 | 22510817 | 13210352 | 1084884 | 372674 | 0 | 61743497.85
0
| 1A - North Wenatchee Avenue |  | 16793597 | 18236277 | 42387 | 355025 | 171110 | 390140 | 484018 | 847816 | 4247499 | 6508572 | 3732152 | 1084884 | 372674 | 0 | 18236277
|  | Preliminary Engineering | 1508008 | 2702352 | 42387 | 355025 | 171110 | 342938 | 282884 | 492149 | 980426 | 35433 | 0 | 0 | 0 | 0 | 2659965
|  | Environmental-Permitting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Right of Way | 1346664 | 1475000 | 0 | 0 | 0 | 47202 | 81134 | 43997 | 486000 | 816667 | 0 | 0 | 0 | 0 | 1475000
|  | Construction Engineering | 2090838.75 | 2108838.75 | 0 | 0 | 0 | 0 | 18000 | 46750.5 | 417160.95 | 848470.8 | 559822.8 | 162732.6 | 55901.1 | 0 | 2108838.75
|  | Construction | 10454193.75 | 10544193.75 | 0 | 0 | 0 | 0 | 90000 | 233752.5 | 2085804.75 | 4242354 | 2799114 | 813663 | 279505.5 | 0 | 10544193.75
|  | Contingency | 1393892.5 | 1405892.5 | 0 | 0 | 0 | 0 | 12000 | 31167 | 278107.3 | 565647.2 | 373215.2 | 108488.4 | 37267.4 | 0 | 1405892.5
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| 1B - McKittrick RR Underpass |  | 31524200 | 38507219.85 | 377818.14 | 1323039 | 955289.07 | 1419079.64 | 2907794 | 1500000 | 5546000 | 15000000 | 9478200 | 0 | 0 | 0 | 38507219.85
|  | Preliminary Engineering | 2046000 | 4330885.85 | 328987.31 | 26369.33 | 276839.21 | 152690 | 1500000 | 1500000 | 546000 | 0 | 0 | 0 | 0 | 0 | 4001898.54
|  | Environmental-Permitting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Right of Way | 0 | 3290340 | 48830.83 | 1296669.67 | 678449.86 | 1266389.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3241509.17
|  | Construction Engineering | 2837000 | 2837000 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000 | 837000 | 0 | 0 | 0 | 2837000
|  | Construction | 23639000 | 25046794 | 0 | 0 | 0 | 0 | 1407794 | 0 | 3000000 | 13000000 | 7639000 | 0 | 0 | 0 | 25046794
|  | Contingency | 3002200 | 3002200 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000 | 1002200 | 0 | 0 | 0 | 3002200
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| 1C - US2 Roundabout |  | 4347096 | 5000001 | 0 | 0 | 3031 | 276959 | 372915 | 48400 | 3296451 | 1002245 | 0 | 0 | 0 | 0 | 5000001
|  | Preliminary Engineering | 6021 |  | 0 | 0 | 3031 | 276959 | 347915 | 6021 | 0 | 0 | 0 | 0 | 0 | 0 | 633926
|  | Environmental-Permitting | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Right of Way | 0 |  | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
|  | Construction Engineering | 651161.25 |  | 0 | 0 | 0 | 0 | 0 | 6356.85 | 494467.65 | 150336.75 | 0 | 0 | 0 | 0 | 651161.25
|  | Construction | 3255806.25 |  | 0 | 0 | 0 | 0 | 0 | 31784.25 | 2472338.25 | 751683.75 | 0 | 0 | 0 | 0 | 3255806.25
|  | Contingency | 434107.5 |  | 0 | 0 | 0 | 0 | 0 | 4237.9 | 329645.1 | 100224.5 | 0 | 0 | 0 | 0 | 434107.5
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
0
#2 Confluence Parkway |  |  | 137949360 | 141157431 | 620000 | 0 | 688071 | 900000 | 1000000 | 4777901 | 19789400 | 20154056 | 56400000 | 32255003 | 4573000 | 0 | 141157431
0
| 2A - Miller Underpass and CP Phase 1 (Hawley St - South) |  | 61087756 | 61837756 | 0 | 0 | 50000 | 200000 | 500000 | 2250000 | 6000000 | 6388428 | 31000000 | 15449328 | 0 | 0 | 61837756
|  | Preliminary Engineering | 4350000 | 5000000 | 0 | 0 | 50000 | 100000 | 500000 | 1850000 | 2500000 | 0 | 0 | 0 | 0 | 0 | 5000000
|  | Environmental-Permitting | 0 | 500000 | 0 | 0 | 0 | 100000 | 400000 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
|  | Right of Way | 9648428 | 9648428 | 0 | 0 | 0 | 0 | 0 | 0 | 6148428 | #REF! | 0 | 0 | 0 | 0 | #REF!
|  | Construction Engineering | 4400000 | 4400000 | 0 | 0 | 0 | 0 | 0 | 0 | 240000 | 3000000 | 1160000 | #REF! | 0 | 0 | #REF!
|  | Construction | 36669000 | 36669000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000000 | 11669000 | #REF! | 0 | 0 | #REF!
|  | Contingency | 5620328 | 5620328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 2620328 | #REF! | 0 | 0 | #REF!
[6 empty] | 0 | 0 | 0 | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | #REF!
0 | bar: 2018 to 2020
| 2B - Confluence Parkway Phase 2 (Hawley St - North) |  | 66861604 | 69269675 | 570000 | 0 | 638071 | 700000 | 500000 | 1727901 | 9189400 | 9165628 | 25400000 | 16805675 | 4573000 | 0 | 69269675
|  | Preliminary Engineering | 4699578 | 5711000 | 320000 | 0 | 208762 | 200000 | 282660 | 1000000 | 3699578 | 0 | 0 | 0 | 0 | 0 | 5391000
|  | Environmental-Permitting | 1053351 | 2450000 | 250000 | 0 | 429309 | 500000 | 217340 | 727901 | 325450 | 0 | 0 | 0 | 0 | 0 | 2200000
|  | Right of Way | 9970000 | 9970000 | 0 | 0 | 0 | 0 | 0 | 5164372 | 4805628 | #REF! | 0 | 0 | 0 | 0 | #REF!
|  | Construction Engineering | 4312700 | 4312700 | 0 | 0 | 0 | 0 | 0 | 0 | 360000 | 2400000 | 1200000 | 352700 | #REF! | 0 | #REF!
|  | Construction | 35939000 | 35939000 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 20000000 | 10000000 | 2939000 | #REF! | 0 | #REF!
|  | Contingency | 10886975 | 10886975 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 3000000 | 5605675 | 1281300 | #REF! | 0 | #REF!
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | bar: 2018 to 2020
| 2C - South End Bike/ Ped Access Bridge |  | 10000000 | 10050000 | 50000 | 0 | 0 | 0 | 0 | 800000 | 4600000 | 4600000 | 0 | 0 | 0 | 0 | 10050000
|  | Preliminary Engineering | 600000 |  | 50000 | 0 | 0 | 0 | 0 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 600000
|  | Environmental-Permitting | 200000 |  | 0 | 0 | 0 | 0 | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 200000
|  | Right of Way | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Construction Engineering | 1040000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 520000 | 520000 | 0 | 0 | 0 | 0 | 1040000
|  | Construction | 5400000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2700000 | 2700000 | 0 | 0 | 0 | 0 | 5400000
|  | Contingency 10% | 2760000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1380000 | 1380000 | 0 | 0 | 0 | 0 | 2760000
0
#3 Cascade Interchange |  |  | 16364756 | 17242134 | 264082 | 139257 | 474039 | 0 | 0 | 741601 | 600216 | 7306266 | 5016969 | 2699704 | 0 | 0 | 17242134
0
| 3A - Hwy Iterchange |  | 16364756 | 16628838 | 264082 | 0 | 0 | 0 | 0 | 741601 | 600216 | 7306266 | 5016969 | 2699704 | 0 | 0 | 16628838
|  | Preliminary Engineering | 1072179 | 1336261 | 264082 | 0 | 0 | 0 | 0 | 635658 | 436521 | 0 | 0 | 0 | 0 | 0 | 1072179
|  | Environmental-Permitting | 269638 | 269638 | 0 | 0 | 0 | 0 | 0 | 105943 | 163695 | 0 | 0 | 0 | 0 | 0 | 269638
|  | Right of Way | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Construction Engineering | 1421912 | 1421912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 843031 | 578881 | 0 | 0 | 0 | 1421912
|  | Construction | 12179115 | 12179115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5620204 | 3859207 | 2699704 | 0 | 0 | 12179115
|  | Contingency | 1421912 | 1421912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 843031 | 578881 | 0 | 0 | 0 | 1421912
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | bar: 2018 to 2019
| 3B - | US2 /SR 28 Roundabouts (35th and 38th) | 0 | 613296 | 0 | 139257 | 474039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 613296
|  | Preliminary Engineering | 0 | 502992 | 0 | 139257 | 363735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 502992
|  | Environmental-Permitting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Right of Way | 0 | 110304 | 0 | 0 | 110304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110304
|  | Construction Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Construction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Contingency | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
#4 Sunset Highway/ SR28 Widening |  |  | 55857089 | 66122010 | 7619794 | 3243 | 308122 | 2333762 | 6083766 | 9333764 | 6333764 | 7705795 | 11400000 | 10000000 | 5000000 | 0 | 66122010
|  | Preliminary Engineering | 6357087 |  | 219794 | 3243 | 308122 | 1833764 | 1833764 | 1833764 | 1833764 | 855795 | 0 | 0 | 0 | 0 | 8502216
|  | Environmental-Permitting | 0 |  | 6000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Right of Way | 18500002 |  | 0 | 0 | 0 | 499998 | 4250002 | 7500000 | 4500000 | 1500000 | 750000 | 0 | 0 | 0 | 19000000
|  | Construction Engineering | 4650000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 802500 | 1597500 | 1500000 | 750000 | 0 | 4650000
|  | Construction | 23250000 |  | 1400000 | 0 | 0 | 0 | 0 | 0 | 0 | 4012500 | 7987500 | 7500000 | 3750000 | 0 | 23250000
|  | Contingency | 3100000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 535000 | 1065000 | 1000000 | 500000 | 0 | 3100000
0
Cost Grand Total |  |  | 262836098 | 286265072.85 | 8924081.14 | 1820564 | 2599662.07 | 5319940.64 | 10848493 | 17249482 | 39813330 | 57676934 | 86027321 | 46039591 | 9945674 | 0 | 286265072.85
Net Surplus (Defecit) |  |  | 0 |  | -834082 | -859000 | -93899 | -356101 | -650000 | -500000 | -1000000 | 0 | 0 | 0 | 0 | 0 | -3459000
|  | Segment: | 1A | 1B | 2017: 1C; 2018: 2A; 2019: 2B; 2020: 2C; 2021: 3; 2022: 4
|  | Planning Complete | ü | ü | bar: 2017 to 2022
|  | Environmental Review | CE 7/21 | CE 7/21 | 2017: ü; 2018: EA 3/22; 2019: EA 3/22; 2020: CE 6/22; 2021: EISü; 2022: EISü
|  | Preliminary Engineering (% complete) | 10% | 20% | 2017: 30%; 2018: 20%; 2019: 20%; 2020: 10%; 2021: 10%; 2022: 10%
|  | Right-of-Way Complete | 12/22 | ü | 2017: 12/21; 2018: 1/24; 2019: 1/24; 2020: 1/24; 2021: ü; 2022: 12/25
|  | Construction Start Date (quarter) | Q2 ‘23 | Q1 ‘24 | 2017: Q4 ‘21; 2018: Q3 ‘24; 2019: Q3 ‘24; 2020: Q3 ‘23; 2021: Q2 ‘24; 2022: Q4 ‘24
|  | Construction End Date (quarter) | Q4 ‘27 | Q4 ‘26 | 2017: Q4 ‘23; 2018: Q4 ‘26; 2019: Q4 ‘26; 2020: Q1 ‘25; 2021: Q4 ‘26; 2022: Q4 ‘27
|  | Updated schedule - best guess 3/13/21 | Cashflow is close but does not exactly match this new best guess schedule.
Contintues to show all projects complete by Q4 27
if Cascade Hwy EA complete by 3/22 then Obligation can later in 2022 or early 2023. Construction can then begin within 18 months.

## Eligibility Breakdown
Minimum Timeline Requirements
|  | Schedule based on contract date of (obligation): | 2022-11-01
|  | Construction Must Start before (+ 18 Months) | 2024-04-24
|  | Match Starts Counting on | 2021-01-01 | Match counts at project award
Legend
Project Totals
Eligible Future Costs and Sources
Pre-Match Invested
PE and ROW
Construction
Funding Sources
|  | Source | Eligible Future | Total Project
Local
|  | City of Wenatchee | 11000000 | 15134981.0648
|  | Douglas County | 0
|  | Chelan - Douglas Transportation Council | 0
|  | Link | 0
|  | BNSF | 1000000 | 1000000
|  | Other | 1500000
| Local Subtotal |  | 13500000 | 16134981.0648
State
|  | Transit Grant | 0 | 0
|  | FMSIB | 0 | 0
|  | State of Wasington - Other | 31924200 | 31924200
|  | Connecting Washington Sunset Highway | 55857089 | 58522010
|  | Connecting Washington North Wenatchee Ave | 21140693 | 23000001
|  | CERB - Dept. of Commerce | 0 | 138000
|  | Transportation Improvement Board | 0 | 0
|  | State of Wasington - Other | 0 | 8613296
| State Subtotal |  | 108921982 | 122197507
Federal
|  | STP | 0 | 3225386.7853
|  | INFRA | 140414116 | 140414116
0
| Federal Subtotal |  | 140414116 | 143639502.7853
Funding Source Grant Total |  |  | 262836098
Project Costs by Classification Criteria
|  | Sub-project | Future Eligible Costs | Total Project | National Highway Freight Network | National Highway System | Rail-Highway Grade Separation | Notes
#1 North Wenatchee |  |  | 52664893 | 61743497.85
| 1A - North Wenatchee Avenue |  | 16793597 | 18236277 | 16793597 |  |  | North Wen. Ave SR 285 is both NHS and HNFN
|  | Preliminary Engineering | 1508008 | 2702352
|  | Environmental-Permitting | 0 | 0
|  | Right of Way | 1346664 | 1475000
|  | Construction Engineering | 2090838.75 | 2108838.75
|  | Construction | 10454193.75 | 10544193.75
|  | Contingency | 1393892.5 | 1405892.5
| 1B - McKittrick RR Underpass |  | 31524200 | 38507219.85 |  |  | 31524200
|  | Preliminary Engineering | 2046000 | 4330885.85
|  | Environmental-Permitting | 0 | 0
|  | Right of Way | 0 | 3290340
|  | Construction Engineering | 2837000 | 2837000
|  | Construction | 23639000 | 25046794
|  | Contingency | 3002200 | 3002200
| 1C - US2 Roundabout |  | 4347096 | 5000001 |  | 4347096
|  | Preliminary Engineering | 6021
|  | Environmental-Permitting | 0
|  | Right of Way | 0
|  | Construction Engineering | 651161.25
|  | Construction | 3255806.25
|  | Contingency | 434107.5
#2 Confluence Parkway |  |  | 137949360 | 141157431
| 2A - Miller Underpass and CP Phase 1 (Hawley St - South) |  | 61087756 | 61837756 |  |  | 61087756 | Both HFHN and RR Separation
|  | Preliminary Engineering | 4350000 | 5000000
|  | Environmental-Permitting | 0 | 500000
|  | Right of Way | 9648428 | 9648428
|  | Construction Engineering | 4400000 | 4400000
|  | Construction | 36669000 | 36669000
|  | Contingency | 5620328 | 5620328
| 2B - Confluence Parkway Phase 2 (Hawley St - North) |  | 66861604 | 69269675 | 66861604
|  | Preliminary Engineering | 4699578 | 5711000
|  | Environmental-Permitting | 1053351 | 2450000
|  | Right of Way | 9970000 | 9970000
|  | Construction Engineering | 4312700 | 4312700
|  | Construction | 35939000 | 35939000
|  | Contingency | 10886975 | 10886975
| 2C - South End Bike/ Ped Access Bridge |  | 10000000 | 10050000 |  |  | 10000000
|  | Preliminary Engineering | 600000
|  | Environmental-Permitting | 200000
|  | Right of Way | 0
|  | Construction Engineering | 1040000
|  | Construction | 5400000
|  | Contingency 10% | 2760000
#3 Cascade Interchange |  |  | 16364756 | 16628838 |  | 16364756
| 3A - Hwy Iterchange |  | 16364756 | 16628838 |  | 16364756
|  | Preliminary Engineering | 1072179 | 1336261
|  | Environmental-Permitting | 269638 | 269638
|  | Right of Way | 0 | 0
|  | Construction Engineering | 1421912 | 1421912
|  | Construction | 12179115 | 12179115
|  | Contingency | 1421912 | 1421912
|  | Preliminary Engineering | 0 | 502992
|  | Environmental-Permitting | 0 | 0
|  | Right of Way | 0 | 110304
|  | Construction Engineering | 0 | 0
|  | Construction | 0 | 0
|  | Contingency | 0 | 0
#4 Sunset Highway/ SR28 Widening |  |  | 55857089 | 66122010 |  | 55857089
|  | Preliminary Engineering | 6357087
|  | Environmental-Permitting | 0
|  | Right of Way | 18500002
|  | Construction Engineering | 4650000
|  | Construction | 23250000
|  | Contingency | 3100000
Cost Grand Total |  |  | 262836098 | 285651776.85 | 83655201 | 92933697 | 102611956
Net Surplus (Defecit)
[9 empty] | Funding Source | Status | Amount | Description
[9 empty] | State of WA (Connecting WA) | Secured | 76997782 | 2015 Connecting Washington is State Gas Tax (11.9 cents)
[9 empty] | State of WA (Nickel Package) | Secured | 0 | 2003 Nickel Package State Gas Tax (5 cents)
[9 empty] | BNSF | Secured | 1000000 | Required 5% when replacing at-grade x-ing with grade separation
[9 empty] | City of Wenatchee | Secured | 11000000 | Includes city tax, public partnerships, state and local grants/loans
[9 empty] | Link Transit | Secured | 0 | Link Transit Sales Tax
[9 empty] | Other Local/State | Secured | 1500000 | CERB and PWTF State Loans
[9 empty] | Surface Transportation Program | Secured | 0 | Federal Funding already obligated
[9 empty] | State of Washington (2020) | Requested | 31924200 | Requested of the State Legislature
[9 empty] | Total |  | 122421982
[11 empty] | 90497782 | Local funding before State Request

## Funding Source Summary
Schedule for the Apple Capital Loop Network of Projects
Minimum Timeline Requirements
|  | Schedule based on contract date of (obligation): | 2022-11-01
|  | Construction Must Start before (+ 18 Months) | 2024-04-24
|  | Match Starts Counting on | 2020-09-30 | Match counts at project award
Legend
Project Totals
Eligible Future Costs and Sources
Pre-Match Invested
PE and ROW
Construction
Funding Sources
|  | Source | Eligible Future | Total Project
Local
|  | City of Wenatchee | 11000000 | 15134981.0648
|  | Douglas County | 0
|  | Chelan - Douglas Transportation Council | 0
|  | Link | 0
|  | BNSF | 1000000 | 1000000
|  | Other | 1500000 | 3059000
| Local Subtotal |  | 13500000 | 19193981.0648
State
|  | Transit Grant | 0 | 0
|  | FMSIB | 0 | 0
|  | State of Wasington - Requested | 31924200 | 31924200
|  | Connecting Washington Sunset Highway | 55857089 | 58522010
|  | Connecting Washington North Wenatchee Ave | 21140693 | 23000001
|  | CERB - Dept. of Commerce | 0 | 138000
|  | Transportation Improvement Board | 0 | 0
|  | State of Wasington - Other | 0 | 8613296
| State Subtotal |  | 108921982 | 122197507
Federal
|  | STP | 0 | 3225386.7853
|  | INFRA | 140414116 | 140414116
0
| Federal Subtotal |  | 140414116 | 143639502.7853
Funding Source Grant Total |  |  | 262836098 | 285030990.85 | 0 | 0
|  |  |  | 22194892.85 | [8 empty] | Full Project | INFRA | Local Secured | State Request
Project Costs, INFRA Request, and Match | [12 empty] | Future eligible
|  | Sub-project | Future Eligible | Total Project | INFRA Request | Match
#1 North Wenatchee |  |  | 52664893 | 61743497.85 | 21000000 | 31664893 | [5 empty] | #1 North Wenatchee | 52664893 | 21000000 | 23140693 | 8524200 | 52664893
[12 empty] | INFRA request |  |  |  |  | 0
| 1A - North Wenatchee Avenue |  | 16793597 | 18236277 | 0 | 16793597 | [5 empty] | 1A - North Wenatchee Avenue | 16793597 |  | 16793597 |  | 16793597
|  | Preliminary Engineering | 1508008 | 2702352 |  | 1508008 | [5 empty] | CWA North Wenatchee Avenue | 1508008 |  |  |  | 0
|  | Environmental-Permitting | 0 | 0 |  | 0 | [5 empty] | CWA Sunset Highway | 0 |  |  |  | 0
|  | Right of Way | 1346664 | 1475000 |  | 1346664 | [5 empty] | Inductive Electric Transit Coaches + Increased Frequency | 1346664 |  |  |  | 0
|  | Construction Engineering | 2090838.75 | 2108838.75 |  | 2090838.75 | [5 empty] | BNSF Contribution to Miller Grade Separation | 2090838.75 |  |  |  | 0
|  | Construction | 10454193.75 | 10544193.75 |  | 10454193.75 | [5 empty] | City Match - final increment of NEPA | 10454193.75 |  |  |  | 0
|  | Contingency | 1393892.5 | 1405892.5 |  | 1393892.5 | [5 empty] | Total Match | 1393892.5 |  |  |  | 0
[6 empty] | 0 | [6 empty] | 0 |  |  |  | 0
[6 empty] | 0 | [5 empty] | Total Cost | 0 |  |  |  | 0
| 1B - McKittrick RR Underpass |  | 31524200 | 38507219.85 | 21000000 | 10524200 | [5 empty] | 1B - McKittrick RR Underpass | 31524200 | 21000000 | 2000000 | 8524200 | 31524200
|  | Preliminary Engineering | 2046000 | 4330885.85 |  | 2046000 | [6 empty] | 2046000 | 0 |  |  | 0
|  | Environmental-Permitting | 0 | 0 |  | 0 | [6 empty] | 0 | 0 |  |  | 0
|  | Right of Way | 0 | 3290340 |  | 0 | [6 empty] | 0 | 0 |  |  | 0
|  | Construction Engineering | 2837000 | 2837000 |  | 2837000 | [6 empty] | 2837000 | 0 |  |  | 0
|  | Construction | 23639000 | 25046794 |  | 23639000 | [6 empty] | 23639000 | 0 |  |  | 0
|  | Contingency | 3002200 | 3002200 |  | 3002200 | [6 empty] | 3002200 | 0 |  |  | 0
[6 empty] | 0 | [6 empty] | 0 | 0 |  |  | 0
[6 empty] | 0 | [6 empty] | 0 | 0 |  |  | 0
| 1C - US2 Roundabout |  | 4347096 | 5000001 | 0 | 4347096 | [5 empty] | 1C - US2 Roundabout | 4347096 | 0 | 4347096 |  | 4347096
|  | Preliminary Engineering | 6021 | [9 empty] | 6021 | 0 |  |  | 0
|  | Environmental-Permitting | 0 | [9 empty] | 0 | 0 |  |  | 0
|  | Right of Way | 0 | [9 empty] | 0 | 0 |  |  | 0
|  | Construction Engineering | 651161.25 | [9 empty] | 651161.25 | 0 |  |  | 0
|  | Construction | 3255806.25 | [9 empty] | 3255806.25 | 0 |  |  | 0
|  | Contingency | 434107.5 | [9 empty] | 434107.5 | 0 |  |  | 0
[13 empty] | 0 | 0 |  |  | 0
[13 empty] | 0 | 0 |  |  | 0
[13 empty] | 0 | 0 |  |  | 0
#2 Confluence Parkway |  |  | 137949360 | 141157431 | 103049360 | 34900000 | [5 empty] | #2 Confluenence Parkway | 137949360 | 103049360 | 11500000 | 23400000 | 137949360 | 0 | 34900000
[13 empty] | 0 | 0 |  |  | 0 | 0
| 2A - Miller Underpass and CP Phase 1 (Hawley St - South) |  | 61087756 | 61837756 | 53587756 | 7500000 | [5 empty] | 2A - Miller Underpass and CP Phase 1 (Hawley St - South) | 61087756 | 53587756 | 7500000 |  | 61087756 | 0
|  | Preliminary Engineering | 4350000 | 5000000 | [8 empty] | 4350000 | 0 |  |  | 0 | -4350000
|  | Environmental-Permitting | 0 | 500000 | [8 empty] | 0 | 0 |  |  | 0 | 0
|  | Right of Way | 9648428 | 9648428 | [8 empty] | 9648428 | 0 |  |  | 0 | -9648428
|  | Construction Engineering | 4400000 | 4400000 | [8 empty] | 4400000 | 0 |  |  | 0 | -4400000
|  | Construction | 36669000 | 36669000 | [8 empty] | 36669000 | 0 |  |  | 0 | -36669000
|  | Contingency | 5620328 | 5620328 | [8 empty] | 5620328 | 0 |  |  | 0 | -5620328
[13 empty] | 0 | 0 |  |  | 0 | 0
[13 empty] | 0 | 0 |  |  | 0 | 0
| 2B - Confluence Parkway Phase 2 (Hawley St - North) |  | 66861604 | 69269675 | 39461604 | 27400000 | [5 empty] | 2B - Confluence Parkway Phase 2 (Hawley St - North) | 66861604 | 39461604 | 4000000 | 23400000 | 66861604 | 0
|  | Preliminary Engineering | 4699578 | 5711000 |  | 4699578 | [6 empty] | 4699578 | 0 |  |  | 0 | -4699578
|  | Environmental-Permitting | 1053351 | 2450000 |  | 1053351 | [6 empty] | 1053351 | 0 |  |  | 0 | -1053351
|  | Right of Way | 9970000 | 9970000 |  | 9970000 | [6 empty] | 9970000 | 0 |  |  | 0 | -9970000
|  | Construction Engineering | 4312700 | 4312700 |  | 4312700 | [6 empty] | 4312700 | 0 |  |  | 0 | -4312700
|  | Construction | 35939000 | 35939000 |  | 35939000 | [6 empty] | 35939000 | 0 |  |  | 0 | -35939000
|  | Contingency | 10886975 | 10886975 |  | 10886975 | [6 empty] | 10886975 | 0 |  |  | 0 | -10886975
[6 empty] | 0 | [6 empty] | 0 | 0 |  |  | 0 | 0
[6 empty] | 0 | [6 empty] | 0 | 0 |  |  | 0 | 0
| 2C - South End Bike/ Ped Access Bridge |  | 10000000 | 10050000 | 10000000 | 0 | [5 empty] | 2C - South End Bike/ Ped Access Bridge | 10000000 | 10000000 | 0 |  | 10000000 | 0
|  | Preliminary Engineering | 600000 | [9 empty] | 600000 | 0 |  |  | 0 | -600000
|  | Environmental-Permitting | 200000 | [9 empty] | 200000 | 0 |  |  | 0 | -200000
|  | Right of Way | 0 | [9 empty] | 0 | 0 |  |  | 0 | 0
|  | Construction Engineering | 1040000 | [9 empty] | 1040000 | 0 |  |  | 0 | -1040000
|  | Construction | 5400000 | [9 empty] | 5400000 | 0 |  |  | 0 | -5400000
|  | Contingency 10% | 2760000 | [9 empty] | 2760000 | 0 |  |  | 0 | -2760000
[13 empty] | 0 | 0 |  |  |  | 0
#3 Cascade Interchange |  |  | 16364756 | 17242134 | 16364756 | 0 | [5 empty] | #3 Cascade Interchange | 16364756 | 16364756 |  |  | 16364756 | 0
[13 empty] | 0 | 0 |  |  | 0 | 0
| 3A - Hwy Iterchange |  | 16364756 | 16628838 | 16364756 | 0 | [5 empty] | 3A - Hwy Iterchange | 16364756 | 16364756 |  |  | 16364756 | 0
|  | Preliminary Engineering | 1072179 | 1336261 | [8 empty] | 1072179 | 0 |  |  | 0 | -1072179
|  | Environmental-Permitting | 269638 | 269638 | [8 empty] | 269638 | 0 |  |  | 0 | -269638
|  | Right of Way | 0 | 0 | [8 empty] | 0 | 0 |  |  | 0 | 0
|  | Construction Engineering | 1421912 | 1421912 | [8 empty] | 1421912 | 0 |  |  | 0 | -1421912
|  | Construction | 12179115 | 12179115 | [8 empty] | 12179115 | 0 |  |  | 0 | -12179115
|  | Contingency | 1421912 | 1421912 | [8 empty] | 1421912 | 0 |  |  | 0 | -1421912
[13 empty] | 0 | 0 |  |  | 0 | 0
[13 empty] | 0 | 0 |  |  | 0 | 0
| 3B - | US2 /SR 28 Roundabouts (35th and 38th) | 0 | 613296 | 0 | 0 | [5 empty] | 3B - US2 /SR 28 Roundabouts (35th and 38th) | 0 | 0 |  |  |  | 0
|  | Preliminary Engineering | 0 | 502992 | [8 empty] | 0 | 0 |  |  |  | 0
|  | Environmental-Permitting | 0 | 0 | [8 empty] | 0 | 0 |  |  |  | 0
|  | Right of Way | 0 | 110304 | [8 empty] | 0 | 0 |  |  |  | 0
|  | Construction Engineering | 0 | 0 | [8 empty] | 0 | 0 |  |  |  | 0
|  | Construction | 0 | 0 | [8 empty] | 0 | 0 |  |  |  | 0
|  | Contingency | 0 | 0 | [8 empty] | 0 | 0 |  |  |  | 0
[13 empty] | 0 | 0 |  |  |  | 0
[13 empty] | 0 | 0 |  |  |  | 0
#4 Sunset Highway/SR28 Widening |  |  | 55857089 | 66122010 | 0 | 55857089 | [5 empty] | #4 Sunset Highway/SR28 Widening | 55857089 | 0 | 55857089 |  | 55857089 | 0
|  | Preliminary Engineering | 6357087 | [9 empty] | 6357087 | 0 |  |  | 0 | -6357087
|  | Environmental-Permitting | 0 | [9 empty] | 0 | 0 |  |  | 0 | 0
|  | Right of Way | 18500002 | [9 empty] | 18500002 | 0 |  |  | 0 | -18500002
|  | Construction Engineering | 4650000 | [9 empty] | 4650000 | 0 |  |  | 0 | -4650000
|  | Construction | 23250000 | [9 empty] | 23250000 | 0 |  |  | 0 | -23250000
|  | Contingency | 3100000 | [9 empty] | 3100000 | 0 |  |  | 0 | -3100000
[13 empty] | 0 | 0 |  |  | 0 | 0
Cost Grand Total |  |  | 262836098 | 286265072.85 | 140414116 | 122421982 | [6 empty] | 262836098 | 140414116 | 90497782 | 31924200 | 262836098 | 0
Net Surplus (Defecit) | [11 empty] | INFRA request | 140414116
[6 empty] | 262836098 | [5 empty] | Local Match | 122421982 |  |  | 122421982 | 0
[5 empty] | 53.42% | 46.58% | [7 empty] | 53.42% | 34.43% | 12.15%
|  |  |  | 23428974.85 | [11 empty] | 46.58%
[7 empty] | Funding Source | Status | Amount | Description | Match Calc.
[7 empty] | State of WA (Connecting WA) | Secured | 76997782 | 2015 Connecting Washington is State Gas Tax (11.9 cents) | 29.29%
|  | Segment (Subproject) | Responsible Agency | INFRA Request | Project Total Future Eligible Costs |  | State of WA (Nickel Package) | Secured | 0 | 2003 Nickel Package State Gas Tax (5 cents) | 0%
|  | Segment 1A – N. Wen. Ave. | WSDOT |  | 16793597 |  | BNSF | Secured | 1000000 | Required 5% when replacing at-grade x-ing with grade separation | 0.3805%
|  | Segment 1B – McKittrick Underpass | City of Wenatchee | 21000000 | 31524200 |  | City of Wenatchee | Secured | 11000000 | Includes city tax, public partnerships, state and local grants/loans | 4.185%
|  | Segment 1C – US 2 Roundabout | WSDOT |  | 4347096 |  | Link Transit | Secured | 0 | Link Transit Sales Tax
|  | Segment 2A – Confluence Pkwy South | City of Wenatchee | 53587756 | 61087756 |  | Other Local/State | Secured | 1500000 | CERB and PWTF State Loans to City
|  | Segment 2B – Confluence Pkwy North | City of Wenatchee | 39461604 | 66861604 |  | Surface Transportation Program | Secured | 0 | Federal Funding already obligated | 0%
|  | Segment 2C – South End Bike/ Ped Access Bridge | City of Wenatchee | 10000000 | 10000000 |  | State of Washington (2020) | Requested | 31924200 | Requested of the State Legislature | 12.15%
|  | Segment 3 – Cascade Interchange | Douglas County | 16364756 | 16364756 |  | Total |  | 122421982
|  | Segment 4 – Sunset Hwy / SR 28 Widening | WSDOT |  | 55857089 |  | Non-Federal Match |  | 122421982 | 46.58%
|  | Total |  | 140414116 | 262836098 |  | Federal Match |  | 0 | 0%
|  | Future Eligible Costs | In $ Millions | % |  |  | Total Federal |  | 140414116 | 53.42%
|  | INFRA Request | 140.4141 | 53.42%
|  | Surface Transportation Program | 0 | 0%
|  | Total Federal | 140.4141 | 53.42%
|  | City of Wenatchee/Local | 12.5 | 4.756%
|  | BNSF | 1 | 0.3805%
|  | State of WA | 108.922 | 41.44%
|  | Total Non-Federal Match | 122.422 | 46.58%
|  | Total Funding | 262.8361 | 100%
|  | Match Sources | Source | In $ Millions | % | Status
|  | Surface Transportation Program | Federal | 0 | 0% | City Spent
Local:
|  | State of WA (Connecting WA) | State | 76.9978 | 62.9% | WSDOT Secured
|  | BNSF | Private | 1 | 0.8168% | Required
|  | City of Wenatchee | Local | 11 | 8.985% | Secured
|  | Link Transit | Local | 0 | 0% | Secured
|  | Other Local (Loans) | Local | 1.5 | 1.225% | Secured
|  | State of Washington (2020) | State | 31.9242 | 26.08% | Requested
|  | Total Local |  | 122.422 | 100%
|  | Total Match Funding |  | 122.422 | 100%

## Independent Utility
Schedule for the Apple Capital Loop Network of Projects
Minimum Timeline Requirements
|  | Schedule based on contract date of (obligation): | 2023-11-01
|  | Construction Must Start before (+ 18 Months) | 2025-04-24
|  | Match Starts Counting on | 2022-01-01 | Match counts at project award
Legend
Project Totals
Eligible Future Costs and Sources
Pre-Match Invested
PE and ROW
Construction
Funding Sources
|  | Source | Eligible Future | Total Project
Local
|  | City of Wenatchee | 11000000 | 15134981.0648 |  |  |  |  | 11000000
|  | Douglas County | 0
|  | Chelan - Douglas Transportation Council | 0
|  | Link | 0
|  | BNSF | 1000000 | 1000000 |  |  |  |  | 1000000
|  | Other | 1500000 | [5 empty] | 1500000
| Local Subtotal |  | 13500000 | 16134981.0648
State
|  | Transit Grant | 0 | 0
|  | FMSIB | 0 | 0
|  | State of Wasington - Other | 31924200 | 31924200 |  |  |  |  | 31924200
|  | Connecting Washington Sunset Highway | 55857089 | 58522010 |  |  |  |  | 76997782
|  | Connecting Washington North Wenatchee Ave | 21140693 | 23000001
|  | CERB - Dept. of Commerce | 0 | 138000
|  | Transportation Improvement Board | 0 | 0
|  | State of Wasington - Other | 0 | 8613296
| State Subtotal |  | 108921982 | 122197507 |  |  |  |  | 122421982
Federal
|  | STP | 0 | 3225386.7853
|  | INFRA | 140414116 | 140414116
0
| Federal Subtotal |  | 140414116 | 143639502.7853
Funding Source Grant Total |  |  | 262836098 |  | 0 |  | 0
Independent Utility Matrix - by Funding Source
|  | Sub-project | Future Eligible | Total Project | INFRA Request | Secured Match | Requested Match
#1 North Wenatchee |  |  | 52664893 | 61743497.85 | 21000000 | 23140693 | 8524200 | 52664893 |  |  |  | 23140693
| 1A - North Wenatchee Avenue |  | 16793597 | 18236277 | 0 | 16793597 | 0
|  | Preliminary Engineering | 1508008 | 2702352 |  | 1508008
|  | Environmental-Permitting | 0 | 0 |  | 0
|  | Right of Way | 1346664 | 1475000 |  | 1346664
|  | Construction Engineering | 2090838.75 | 2108838.75 |  | 2090838.75
|  | Construction | 10454193.75 | 10544193.75 |  | 10454193.75
|  | Contingency | 1393892.5 | 1405892.5 |  | 1393892.5
0
0
| 1B - McKittrick RR Underpass |  | 31524200 | 38507219.85 | 21000000 | 2000000 | 8524200
|  | Preliminary Engineering | 2046000 | 4330885.85 |  | 2046000
|  | Environmental-Permitting | 0 | 0 |  | 0
|  | Right of Way | 0 | 3290340 |  | 0
|  | Construction Engineering | 2837000 | 2837000 |  | 2837000
|  | Construction | 23639000 | 25046794 |  | 23639000
|  | Contingency | 3002200 | 3002200 |  | 3002200
0
0
| 1C - US2 Roundabout |  | 4347096 | 5000001 | 0 | 4347096 | 0
|  | Preliminary Engineering | 6021
|  | Environmental-Permitting | 0
|  | Right of Way | 0
|  | Construction Engineering | 651161.25
|  | Construction | 3255806.25
|  | Contingency | 434107.5
#2 Confluence Parkway |  |  | 137949360 | 141157431 | 103049360 | 11500000 | 23400000 | 137949360 | 137549360 | 141157431
| 2A & 2B Confluence Parkway |  | 127949360 | 131107431 | 93049360 | 11500000 | 23400000 |  | 127549360 | 131107431
|  | Preliminary Engineering | 4350000 | 5000000 |  | 4350000 |  | 2A | 60687756 | 61837756
|  | Environmental-Permitting | 0 | 500000 |  | 0
|  | Right of Way | 9648428 | 9648428 |  | 9648428
|  | Construction Engineering | 4400000 | 4400000 |  | 4400000
|  | Construction | 36669000 | 36669000 |  | 36669000
|  | Contingency | 5620328 | 5620328 |  | 5620328
0
0
|  | Preliminary Engineering | 4699578 | 5711000 |  | 4699578 |  | 2B | 66861604 | 69269675
|  | Environmental-Permitting | 1053351 | 2450000 |  | 1053351
|  | Right of Way | 9970000 | 9970000 |  | 9970000
|  | Construction Engineering | 4312700 | 4312700 |  | 4312700
|  | Construction | 35939000 | 35939000 |  | 35939000
|  | Contingency | 10886975 | 10886975 |  | 10886975
0
0
| 2C - South End Bike/Ped Access Bridge |  | 10000000 | 10050000 | 10000000 | 0 | 0 |  | 10000000 | 10050000
|  | Preliminary Engineering | 600000
|  | Environmental-Permitting | 200000
|  | Right of Way | 0
|  | Construction Engineering | 1040000
|  | Construction | 5400000
|  | Contingency 10% | 2760000
#3 Cascade Interchange |  |  | 16364756 | 17242134 | 16364756 | 0 | 0 | 16364756
| 3A - Hwy Iterchange |  | 16364756 | 17242134 | 16364756 | 0 | 0
|  | Preliminary Engineering | 1072179 | 1336261
|  | Environmental-Permitting | 269638 | 269638
|  | Right of Way | 0 | 0
|  | Construction Engineering | 1421912 | 1421912
|  | Construction | 12179115 | 12179115
|  | Contingency | 1421912 | 1421912
|  | Preliminary Engineering | 0 | 502992
|  | Environmental-Permitting | 0 | 0
|  | Right of Way | 0 | 110304
|  | Construction Engineering | 0 | 0
|  | Construction | 0 | 0
|  | Contingency | 0 | 0
#4 Sunset Highway/SR28 Widening |  |  | 55857089 | 66122010 | 0 | 55857089 | 0 | 55857089 |  |  |  | 55857089
|  | Preliminary Engineering | 6357087
|  | Environmental-Permitting | 0
|  | Right of Way | 18500002
|  | Construction Engineering | 4650000
|  | Construction | 23250000
|  | Contingency | 3100000
Cost Grand Total |  |  | 262836098 | 286265072.85 | 140414116 | 90497782 | 31924200 | 262836098
Net Surplus (Defecit) | [11 empty] | 78997782
|  | Full package |  |  | 0
[5 empty] | 53.42% | 34.43% | 12.15%
[7 empty] | 122421982 | 46.58% |  | Funding Source | Status | Amount | Description
[10 empty] | State of WA (Connecting WA) | Secured | 76997782 | 2015 Connecting Washington is State Gas Tax (11.9 cents)
[6 empty] | 90497782 | 31924200 |  |  | State of WA (Nickel Package) | Secured | 0 | 2003 Nickel Package State Gas Tax (5 cents)
|  | Variance |  |  | 0 | 0 | 0 | 0 |  | BNSF | Secured | 1000000 | Required 5% when replacing at-grade x-ing with grade separation
[10 empty] | City of Wenatchee | Secured | 11000000 | Includes city tax, public partnerships, state and local grants/loans
[6 empty] | 13500000 |  |  | 13500000 | City of Wenatchee | Secured | 1500000 | Remaining portion of PWTf Loan
[10 empty] | Surface Transportation Program | Secured | 0 | Federal Funding already obligated
[6 empty] | 76997782 |  |  |  | State of Washington (2020) | Requested | 31924200 | Requested of the State Legislature in Forward WA Transpo Plan
[6 empty] | 90497782 |  |  |  | Total |  | 122421982
31924200
[6 empty] | 122421982 | [5 empty] | 90497782
[10 empty] | State |  | 108921982
Exhibit A – Current Version
| Project Segments |  | Future Eligible | Total Project | INFRA Request | Secured Match | Requested Match
#1 SR 285/North Wenatchee Ave |  |  | 52664893 | 61743498 | 21000000 | 23140693 | 8524200
| 1A–North Wenatchee Avenue |  | 16793597 | 18236277 | 0 | 16793597 | 0
| 1B–McKittrick/BNSF Underpass |  | 31524200 | 38507220 | 21000000 | 2000000 | 8524200
| 1C–US 2/Easy St Roundabout |  | 4347096 | 5000001 | 0 | 4347096 | 0
#2 Confluence Parkway |  |  | 137549360 | 141157431 | 103049360 | 11500000 | 23400000
| 2A–Confluence Pkwy South |  | 60687756 | 61837756 | 61087756 | 500000 | 0
| 2B–Confluence Pkwy North |  | 66861604 | 69269675 | 31961604 | 11000000 | 23400000
| 2C–South End Ped Access |  | 10000000 | 10050000 | 10000000 | 0 | 0
#3 Cascade Interchange |  |  | 16364756 | 17242134 | 16364756 | 0 | 0
#4 SR 28 / Sunset Highway |  |  | 55857089 | 66122010 | 0 | 55857089 | 0
Cost Grand Total |  |  | 262436098 | 286265073 | 264463476 | 90497782 | 31924200
[5 empty] | 53.4% | 34.4% | 12.1%
Exhibit A – Modified Requested Match Allocation
| Project Segments |  | Future Eligible | Total Project | INFRA Request | Secured Match | Requested Match
#1 SR 285/North Wenatchee Ave |  |  | 52664893 | 61743498 | 29524360 | 23140693 | 0
1A–North Wenatchee Avenue |  |  | 16793597 | 18236277 | 0 | 16793597 | 0
1B–McKittrick/BNSF Underpass |  |  | 31524200 | 38507220 | 29524200 | 2000000 | 0
1C–US 2/Easy St Roundabout |  |  | 4347096 | 5000001 | 0 | 4347096 | 0
#2 Confluence Parkway |  |  | 137949360 | 141157431 | 94525160 | 11500000 | 31924200
2A–Confluence Pkwy South |  |  | 61087756 | 67402673 | 60587756 | 500000 | 0
2B–Confluence Pkwy North |  |  | 66861604 | 73754758 | 23937404 | 11000000 | 31924200
2C–South End Ped Access |  |  | 10000000 | 10050000 | 10000000 | 0 | 0
#3 Cascade Interchange |  |  | 16364756 | 17242134 | 16364756 | 0 | 0
#4 SR 28 / Sunset Highway |  |  | 55857089 | 66122010 | 0 | 55857089 | 0
Cost Grand Total |  |  | 262836098 | 286265073 | 140414116 | 90497782 | 31924200
[5 empty] | 53.4% | 34.4% | 12.1%
Project Phasing Funding Options ( Partical Funding Options
Funding Group |  | Component Description | Future Eligible | Total Project | INFRA Request | Secured Match | Requested Match | Non-Fed Match | BCA
| Apple Capital Loop Network of Project Components |  | 262836098 | 286265072.85 | 140414116 | 90497782 | 31924200 | 46.58% | 1.83 | All Segments
A | #1: No. Wenatchee Ave, #2A: Confluence Parkway South, #2C: South End Bike/ Ped Access Connector and #4: Sunset Highway/ SR28 Widening |  | 193806449 | 207279441 | 103049360 | 67357089 | 23400000 | 46.83% | 2.5 | Seg 1, 2A, 2C and 4
B: | #1A: North Wenatchee Avenue #1C: US 2/Easy St Roundabout #2A: Confluence Parkway South, #2C: South End Bike/ Ped Access Connector and #4:Sunset Highway/ SR28 Widening |  | 148085538 | 166810961 | 70587756 | 77497782 | 0 | 0 | 3.09 | Build 1A, 1C, 2A, 2C and 4
C | #1A: North Wenatchee Avenue #1B: McKittrick/BNSF Underpass #1C: US 2/Easy St Roundabout #2C: South End Bike/ Ped Access Bridge and #4 Sunset Highway |  | 132718693 | 142891685 | 41961604 | 67357089 | 23400000 | 68.38% | 2.55 | Build 1A, 1B,1C, 2C and 4
Note on G61: Jeannie Beckett: $500K BNSF +$1.5M remaining portion fo PWTf load
Note on G82: Jeannie Beckett: $11M City funds + $500K BNSF

## 1 North Wenatchee Ave
North Wenatchee Avenue - Network Project #1
Legend
Project Totals
Eligible Future Costs and Sources
Pre-Match Invested
PE and ROW
|  | Construction | [6 empty] | <= Pre-Match | Match =>
Funding Sources
|  | Source | Eligible Future | Total Project | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | Total By Source 2018-2027
Local | [16 empty] | 0
|  | City of Wenatchee | 0 | 2121910.0647 | 2017: 249092.4489; 2018: 479309.265; 2019: 205963.9094; 2020: 147492.2514; 2021: 1040052.19 | 1872817.6158
|  | Douglas County | 0 | 0 | [12 empty] | 0
|  | Chelan - Douglas Transportation Council | 0 | 0 | [12 empty] | 0
|  | Link | 0 | 200000 | 2020: 50000; 2021: 150000 | 200000
|  | BNSF | 500000 | 500000 | 2025: 500000 | 500000
|  | Other | 1500000 | 3059000 | 2018: 859000; 2019: 93899; 2020: 106101; 2021: 500000; 2022: 500000; 2023: 1000000 | 3059000
|  |  | 0 | [13 empty] | 0
| Local Subtotal |  | 2000000 | 5880910.0647 | 249092.4489 | 1338309.265 | 299862.9094 | 303593.2514 | 1690052.19 | 500000 | 1000000 | 0 | 500000 | 0 | 0 | 0 | 5631817.6158
State | [16 empty] | 0
|  | Transit Grant | 0 | [13 empty] | 0
|  | FMSIB | 0 | 0 | [12 empty] | 0
|  | State of Washington - Requested | 8524200 | 8524200 | 2023: 546000; 2024: 3000000; 2025: 4978200 | 8524200
|  | Connecting Washington Sunset Highway | 0 | 0 | [12 empty] | 0
|  | Connecting Washington North Wenatchee Avenue | 21140693 | 23000001 | 0 | 163576 | 171700 | 667099 | 856933 | 896216 | 7543950 | 7510817 | 3732152 | 1084884 | 372674 |  | 23000001
|  | CERB - Dept. of Commerce | 0 | 113000 | 2018: 113000 | 113000
|  | Transportation Improvement Board | 0 | 0 | [12 empty] | 0
|  | State of Washington - Other | 0 | 0
0
| State Subtotal |  | 29664893 | 31637201 | 0 | 276576 | 171700 | 667099 | 856933 | 896216 | 8089950 | 10510817 | 8710352 | 1084884 | 372674 | 0 | 31637201
Federal | [16 empty] | 0
|  | STP | 0 | 3225386.7853 | 2017: 171112.6911; 2018: 63178.735; 2019: 657867.1605; 2020: 1115486.3886; 2021: 1217741.81; 2022: 0; 2023: 0 | 3054274.0942
|  | INFRA | 21000000 | 21000000 | 2022: 1000000; 2023: 4000000; 2024: 12000000; 2025: 4000000 | 21000000
0
0
| Federal Subtotal |  | 21000000 | 24225386.7853 | 171112.6911 | 63178.735 | 657867.1605 | 1115486.3886 | 1217741.81 | 1000000 | 4000000 | 12000000 | 4000000 | 0 | 0 | 0 | 24054274.0941
0
Funding Source Grant Total |  |  | 52664893 | 61743497.85 | 420205.14 | 1678064 | 1129430.07 | 2086178.64 | 3764727 | 2396216 | 13089950 | 22510817 | 13210352 | 1084884 | 372674 | 0 | 61323292.71
Project Costs
|  | Sub-project | Future Eligible | Total Project | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | Total By Phase
0 | bar: 2017
#1 North Wenatchee |  |  | 52664893 | 420205.14 | 2017: 420205.14 | 0
| 1A - North Wenatchee Avenue |  | 16793597 | 18236277 | 42387 | 355025 | 171110 | 390140 | 484018 | 847816 | 4247499 | 6508572 | 3732152 | 1084884 | 372674 | 0 | 18193890
|  | Preliminary Engineering | 1508008 | 2702352 | 42387 | 355025 | 171110 | 342938 | 282884 | 492149 | 980426 | 35433 | 0 | 0 | 0 |  | 2659965
|  | Environmental-Permitting | 0 | 0 | [12 empty] | 0 | bar: 2017
|  | Right of Way | 1346664 | 1475000 |  |  |  | 47202 | 81134 | 43997 | 486000 | 816667 | 0 | 0 | 0 |  | 1475000
|  | Construction Engineering | 2090838.75 | 2108838.75 | 2021: 18000; 2022: 46750.5; 2023: 417160.95; 2024: 848470.8; 2025: 559822.8; 2026: 162732.6; 2027: 55901.1 | 2108838.75
|  | Construction | 10454193.75 | 10544193.75 |  |  |  |  | 90000 | 233752.5 | 2085804.75 | 4242354 | 2799114 | 813663 | 279505.5 | 0 | 10544193.75
|  | Contingency | 1393892.5 | 1405892.5 | 2021: 12000; 2022: 31167; 2023: 278107.3; 2024: 565647.2; 2025: 373215.2; 2026: 108488.4; 2027: 37267.4 | 1405892.5
0 | bar: 2017
0 | bar: 2017
| 1B - McKittrick RR Underpass and McK./Wen. Signal |  | 31524200 | 38507219.85 | 377818.14 | 1323039 | 955289.07 | 1419079.64 | 2907794 | 1500000 | 5546000 | 15000000 | 9478200 | 0 | 0 | 0 | 38129401.71
|  | Preliminary Engineering | 2046000 | 4330885.85 | 328987.31 | 26369.33 | 276839.21 | 152690 | 1500000 | 1500000 | 546000 | 0 | 0 |  |  |  | 4001898.54
|  | Environmental-Permitting | 0 | 0 | [12 empty] | 0 | bar: 2017
|  | Right of Way | 0 | 3290340 | 48830.83 | 1296669.67 | 678449.86 | 1266389.64 | 0 | 0 | 0 | 0 | 0 |  |  |  | 3241509.17
|  | Construction Engineering | 2837000 | 2837000 | 2023: 1000000; 2024: 1000000; 2025: 837000 | 2837000
|  | Construction | 23639000 | 25046794 | 0 | 0 | 0 | 0 | 1407794 | 0 | 3000000 | 13000000 | 7639000 |  |  |  | 25046794
|  | Contingency | 3002200 | 3002200 | 2023: 1000000; 2024: 1000000; 2025: 1002200 | 3002200
|  |  | 0 | [13 empty] | 0 | bar: 2017
0 | bar: 2017
| 1C - US2 Roundabout |  | 4347096 | 5000001 | 0 | 0 | 3031 | 276959 | 372915 | 48400 | 3296451 | 1002245 | 0 | 0 | 0 | 0 | 5000001
|  | Preliminary Engineering | 6021 | 633926 | 2019: 3031; 2020: 276959; 2021: 347915; 2022: 6021; 2023: 0; 2024: 0 | 633926
|  | Environmental-Permitting | 0 | 0 | [12 empty] | 0 | bar: 2017
|  | Right of Way | 0 | 25000 | 2021: 25000 | 25000
|  | Construction Engineering | 651161.25 | 651161.25 | 2022: 6356.85; 2023: 494467.65; 2024: 150336.75 | 651161.25
|  | Construction | 3255806.25 | 3255806.25 | 2022: 31784.25; 2023: 2472338.25; 2024: 751683.75 | 3255806.25
|  | Contingency | 434107.5 | 434107.5 | 2022: 4237.9; 2023: 329645.1; 2024: 100224.5 | 434107.5
0 | bar: 2017
0 | bar: 2017
0 | bar: 2017
0
Cost Grand Total |  |  | 52664893 | 61743497.85 | 420205.14 | 1678064 | 1129430.07 | 2086178.64 | 3764727 | 2396216 | 13089950 | 22510817 | 13210352 | 1084884 | 372674 | 0 | 61323292.71
Net Surplus (Defecit) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 52616493 | 61783152 | 2020: 652905
|  |  | 48400 | -39654.15
|  |  | Total Infra |  | 2018: 21000000
|  |  | Total Eligible Match - Future Costs (Non-Fed) |  | 2018: 31664893
|  |  | Total Eligible Match - Future Costs (Federal) |  | 2018: 0
Segment 1A - Conecting Washington North Wenatchee Avenue
[6 empty] | All Previous | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028
[5 empty] | PE |  | 163576 | 168669 | 342938 | 282884 | 492149 | 980426 | 35433 | 0 | 0 | 0
[5 empty] | RW | 0 | 0 | 0 | 47202 | 81134 | 43997 | 486000 | 816667 | 0 | 0 | 0
[5 empty] | CN | 0 | 0 | 0 | 0 | 120000 | 311670 | 2781073 | 5656472 | 3732152 | 1084884 | 372674
[5 empty] | Total | 0 | 163576 | 168669 | 390140 | 484018 | 847816 | 4247499 | 6508572 | 3732152 | 1084884 | 372674
Segment 1C -Conecting Washington - US 2 and Easy Street
[5 empty] | PE |  | 2019: 3031; 2020: 276959; 2021: 347915; 2022: 6021
[5 empty] | RW |  | 2021: 25000
[5 empty] | CN |  | 2022: 42379; 2023: 3296451; 2024: 1002245
[5 empty] | Total | 0 | 0 | 3031 | 276959 | 372915 | 48400 | 3296451 | 1002245 | 0 | 0 | 0 | 0
|  | Segment 1B -McKittrick Signal Project |  |  |  | All Previous | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028
STP
[5 empty] | PE | 148891.71 | 2018: 26248.08; 2019: 22090.21
[5 empty] | RW | 48830.83 | 2018: 46669.67; 2019: 678449.86; 2020: 1098389.64
[5 empty] | CN |  | 2021: 770000
[5 empty] | Total | 197722.54 | 72917.75 | 700540.07 | 1098389.64 | 770000 | 0 | 0 | 0
Segment 1B - McKittrick Median Project
STP
[5 empty] | PE | 95.6 | 2018: 121.25; 2019: 60000; 2020: 23190
[5 empty] | RW |  | 2020: 168000
[5 empty] | CN |  | 2021: 637794
[5 empty] | Total | 95.6 | 121.25 | 60000 | 191190 | 637794 | 0 | 0 | 0
Segment 1B - McKittrick Underpass, Miller Roundabout, Miller Re-align
|  | PWTF Loan and CERB Loan |  |  | PE | 180000 | 2019: 194749; 2020: 129500; 2021: 1500000; 2022: 1500000; 2023: 546000
Permitting
[5 empty] | RW |  | 2018: 1250000; 2020: 0; 2021: 0; 2022: 0; 2023: 0; 2024: 0
[5 empty] | CN |  | 2023: 5000000; 2024: 15000000; 2025: 9478200
[5 empty] | Total | 180000 | 1250000 | 194749 | 129500 | 1500000 | 1500000 | 5546000 | 15000000
Additional contingency
Total Contingency
[11 empty] | 10% | OPC-C | 2149000
[12 empty] | Proj contingency | 3002200
[13 empty] | 5151200 | 21.79%
Note on J12: Steve King: Est. $1m to keep project design going - while waiting for state funding - City $ to fund NEPA $ was allocated
Note on D17: Steve King: Remaining portion of PWTf Loan
Note on G17: Windows User: CERB Righ of way purchase
Note on H17: Steve King: PTWF Design $ - project 1804
Note on I17: Steve King: PWTF Design $ project 1804
Note on J17: Steve King: PWTF Loan for Miller Re-align. Requires R
Note on K17: Steve King: PTWF Loan for Miller Realign and Util
Note on L17: Steve King: PWTF Loan
Note on G26: Steve King: Dept. of Commerce Grant for Early ROW Acq. For McK.
Note on F46: Windows User: Form and Function plus McK expenditures through 2017 + KPG predesign
Note on G46: Windows User: Connecting WA Plus city funds spent on KPG Pre design less WSDOT reimbursement. Connecting WA is the same as city reimbursement
Note on H46: Windows User: Connecting WA
Note on I46: Steve King: Connect WA
Note on C64: Jeannie Beckett: The schedule of this project was incorrectly stated in BCA as starting in 2018, BCA has been updated to match this Document
Note on F64: Windows User: VE Study
Note on G115: Steve King: Form and Function Study + N. Wen Redev. Plan - 40k funded by CERB
Note on I115: Steve King: From City project 1804. See end of year invoice for KPG 2019.
Note on J115: Steve King: Estimate to Complete KPG Contract under project 1804 for tasks 2 and 3
Note on H117: Steve King: Stemilt Right of Way - Early Acquisition - CERB Loan - $859k and Grant $113k and City balance

## 2 Confluence Parkway
Confluence Parkway
See Map Below
Legend
Project Totals
Eligible Future Costs and Sources
Pre-Match Invested
PE and ROW
|  | Construction | [6 empty] | <= Pre-Match | Match =>
Funding Sources
|  | Source | Eligible Future | Total Project | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | Total By Source 2018-2027
Local | [16 empty] | 0
|  | City of Wenatchee | 11000000 | 13013071 | 2017: 25000; 2019: 288071; 2020: 700000; 2021: 1000000; 2022: 3500000; 2023: 7500000; 2027: 0 | 12988071
|  | Douglas County | 0 | 0 | [12 empty] | 0
|  | Chelan - Douglas Transportation Council | 0 | 570000 | 2017: 570000 | 0
|  | Link | 0 | 200000 | 2020: 200000 | 200000
|  | BNSF | 500000 | 500000 | 2025: 500000 | 500000
|  | Other | 0 | 0
0
| Local Subtotal |  | 11500000 | 14283071 | 595000 | 0 | 288071 | 900000 | 1000000 | 3500000 | 7500000 | 0 | 500000 | 0 | 0 | 0 | 13688071
State | [16 empty] | 0
|  | Transit Grant | 0 | 0 | [12 empty] | 0
|  | FMSIB | 0 | 0 | [12 empty] | 0
|  | State of Washington - Requested | 23400000 | 23400000 | 2024: 7400000; 2025: 16000000 |  | Funding has been requested in Forward WA Bill
|  | Connecting Washington Sunset Highway | 0 | 0 | [12 empty] | 0
|  | Connecting Washington North Wenatchee Avenue | 0 | 0
|  | CERB - Dept. of Commerce | 0 | 25000 | 2017: 25000
|  | Transportation Improvement Board | 0 | 0 | [12 empty] | 0
|  | State of Washington - Other | 0 | 400000 | 2019: 400000
0
| State Subtotal |  | 23400000 | 23825000 | 25000 | 0 | 400000 | 0 | 0 | 0 | 0 | 7400000 | 16000000 | 0 | 0 | 0 | 23800000
Federal | [16 empty] | 0
|  | STP | 0 | 0 | [12 empty] | 0
|  | INFRA | 103049360 | 103049360 | 2022: 1277901; 2023: 12289400; 2024: 12754056; 2025: 39900000; 2026: 32255003; 2027: 4573000 | 103049360
0
0
| Federal Subtotal |  | 103049360 | 103049360 | 0 | 0 | 0 | 0 | 0 | 1277901 | 12289400 | 12754056 | 39900000 | 32255003 | 4573000 | 0 | 103049360
0
Funding Source Grant Total |  |  | 137949360 | 141157431 | 620000 | 0 | 688071 | 900000 | 1000000 | 4777901 | 19789400 | 20154056 | 56400000 | 32255003 | 4573000 | 0 | 140537431
Project Costs
|  | Sub-project | Future Eligible | Total Project | Previous Costs | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | Total By Phase
0
#2 Confluence Parkway | [16 empty] | 0
0
| 2A - Miller Underpass and CP Phase 1 (Miller to Hawley) |  | 61087756 | 61837756 | 0 | 0 | 50000 | 200000 | 500000 | 2250000 | 6000000 | 6388428 | 31000000 | 15449328 | 0 | 0 | 61837756
|  | Preliminary Engineering | 4350000 | 5000000 |  | 2019: 50000; 2020: 100000; 2021: 500000; 2022: 1850000; 2023: 2500000 | 5000000
|  | Environmental-Permitting | 0 | 500000 |  | 2020: 100000; 2022: 400000 | 500000
|  | Right of Way | 9648428 | 9648428 |  | 2023: 3500000; 2024: 6148428 | 9648428
|  | Construction Engineering | 4400000 | 4400000 |  | 2024: 240000; 2025: 3000000; 2026: 1160000 | 4400000
|  | Construction | 36669000 | 36669000 |  | 2025: 25000000; 2026: 11669000 | 36669000
|  | Contingency | 5620328 | 5620328 |  | 2025: 3000000; 2026: 2620328 | 5620328 |  | 13.69%
0
0
| 2B - Confluence Parkway Phase 2 (Hawley St - North) |  | 66861604 | 69269675 | 570000 | 0 | 638071 | 700000 | 500000 | 1727901 | 9189400 | 9165628 | 25400000 | 16805675 | 4573000 | 0 | 68699675
|  | Preliminary Engineering | 4699578 | 5711000 | 320000 | 2019: 208762; 2020: 200000; 2021: 282660; 2022: 1000000; 2023: 3699578 | 5391000
|  | Environmental-Permitting | 1053351 | 2450000 | 250000 | 2018: 0; 2019: 429309; 2020: 500000; 2021: 217340; 2022: 727901; 2023: 325450 | 2200000
|  | Right of Way | 9970000 | 9970000 |  | 2023: 5164372; 2024: 4805628 | 9970000
|  | Construction Engineering | 4312700 | 4312700 |  | 2024: 360000; 2025: 2400000; 2026: 1200000; 2027: 352700 | 4312700
|  | Construction | 35939000 | 35939000 |  | 2024: 3000000; 2025: 20000000; 2026: 10000000; 2027: 2939000 | 35939000
|  | Contingency | 10886975 | 10886975 |  | 2024: 1000000; 2025: 3000000; 2026: 5605675; 2027: 1281300 | 10886975 |  | 27.05%
0
0
0
| #2C South End Bike/ Ped Access Bridge |  | 10000000 | 10050000 | 50000 | 0 | 0 | 0 | 0 | 800000 | 4600000 | 4600000 |  |  |  |  | 10000000
|  | Preliminary Engineering | 600000 | 650000 | 50000 | 2021: 0; 2022: 600000 | 600000
|  | Environmental-Permitting | 200000 | 200000 |  | 2021: 0; 2022: 200000 | 200000
|  | Right of Way | 0 | 0 | 0 | [11 empty] | 0
|  | Construction Engineering | 1040000 | 1040000 |  | 2023: 520000; 2024: 520000 | 1040000
|  | Construction | 5400000 | 5400000 |  | 2023: 2700000; 2024: 2700000 | 5400000
|  | Contingency | 2760000 | 2760000 |  | 2023: 1380000; 2024: 1380000 | 2760000 | 9200000 | 38.12%
0
0
0
0
Cost Grand Total |  |  | 137949360 | 141157431 | 620000 | 0 | 688071 | 900000 | 1000000 | 4777901 | 19789400 | 20154056 | 56400000 | 32255003 | 4573000 | 0 | 140537431 |  |  | 19267303
Net Surplus (Defecit) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Total Infra |  |  | 2018: 103049360; 2019: 74.7%
|  |  | Total Eligible Match - Future Costs (non - Fed) |  |  | 2018: 34900000; 2019: 25.3%; 2020: 55179744
|  |  | Total Eligible Match - Future Costs (Federal) |  |  | 2018: 0
137949360
|  | 154688 | Task 1
|  | 248684 | Task 4
|  | 302000 | Man Reserve
|  | 705372 | design for confluence
1212408
302000
401564
1915972
|  | 1210600 | Environmental excluding design
|  | 200000 | PWTF for N. Wen. For segment 2
|  | 113693 | N. Wen. For segment 2
|  | 2229665 | Check total
2230000
1. There is 15 % Contingency is Opinion of Probable Costs for CN
2. And an Additional 10% Contingency added here to for a Total Contigency of 25%
[6 empty] | 2025: Segment 2A | Segment 2B
[6 empty] | 2025: PE; 2027: 5500000 | PE | 5391000
[6 empty] | 2025: Permitting; 2027: 500000 | Permitting | 2200000
[6 empty] | 2025: RW; 2027: 6148428 | RW | 9970000
[6 empty] | 2025: CN Contract; 2027: 36669000 | CN Contract | 35939000
[6 empty] | 2025: CN Eng; 2027: 4400000 | CN Eng | 4313000
[6 empty] | 2022: FY21 increased contingency; 2025: Proj. Contigency; 2027: 8622736 | Proj. Contigency | 10980307
[6 empty] | 2025: Subtotal CN; 2027: 49691736 | Subtotal CN | 51232307
[6 empty] | 2025: Check total; 2027: 61840164 | Check total | 68793307 |  | 130633471
M w | [5 empty] | 2025: Added contingency FY21; 2027: 3300993; 2028: * |  | 3699007 | * | 3. Added additional Contigency of $7M between 2A and 2B in FY21 as safe guard
[6 empty] | 2027: 58539171 |  | 65094300
[6 empty] | 2025: FY 21 Total Cost; 2027: 61840164 |  | 68793307
130633471
Note on H28: Steve King: Wa St. NEPA Funds
Note on H46: Steve King: Est. of design put into the Miller underpass. Incl. Geotech
Note on I46: Steve King: Est. of design put into Miller - Wen. Ave intersection
Note on I47: Steve King: Included in KPG contract for NEPA
Note on H55: Steve King: Amount of KPG Invoice invested on pre-design
Note on I55: Steve King: Estimate for 2020
Note on H56: Steve King: Based on KPG Invoice for the end of 2019 for project 1804. Confluence Parkway only Task 1 and 4
Note on J65: Jeannie Beckett: moved ped bridge PE out to 2022, added Second Bridge in 2024

## 3 Cascade Int
Cascade Interchange - Wenatchi Landing
Legend
Project Totals
Eligible Future Costs and Sources
Pre-Match Invested
PE and ROW
|  | Construction | [6 empty] | <= Pre-Match | Match =>
Funding Sources
|  | Source | Eligible Future | Total Project | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | Total By Source 2018-2027
Local | [16 empty] | 0
|  | City of Wenatchee | [14 empty] | 0
|  | Douglas Co./Port of Douglas Co. |  | 264082 | 2017: 264082 | 0
|  | Chelan Douglas Trasnportaiton Council | [14 empty] | 0
|  | Link | [14 empty] | 0
|  | BNSF | [14 empty] | 0
|  | Other | [14 empty] | 0
0
| Local Subtotal |  | 0 | 264082 | 264082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
State | [16 empty] | 0
|  | Transit Grant | [14 empty] | 0
|  | FMSIB | [14 empty] | 0
State of Washington - Requested
|  | Connecting Washington Sunset Highway | [14 empty] | 0
|  | Connecting Washington North Wenatchee Avenue | [14 empty] | 0
|  | CERB - Dept. of Commerce | [14 empty] | 0
|  | Transportation Improvement Board | [14 empty] | 0
|  | State of Washington - Other | 0 | 613296 | 2018: 139257; 2019: 474039; 2020: 0; 2021: 0; 2022: 0 | 613296
0
| State Subtotal |  | 0 | 613296 | 0 | 139257 | 474039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 613296
Federal | [16 empty] | 0
|  | STP | [14 empty] | 0
|  | INFRA | 16364756 | 16364756 | 2020: 0; 2021: 0; 2022: 741601; 2023: 600216; 2024: 7306266; 2025: 5016969; 2026: 2699704 | 16364756
0
0
| Federal Subtotal |  | 16364756 | 16364756 | 0 | 0 | 0 | 0 | 0 | 741601 | 600216 | 7306266 | 5016969 | 2699704 | 0 | 0 | 16364756
0
Funding Source Grant Total |  |  | 16364756 | 17242134 | 264082 | 139257 | 474039 | 0 | 0 | 741601 | 600216 | 7306266 | 5016969 | 2699704 | 0 | 0 | 16978052
Project Costs
|  | Sub-project | Future Eligible | Total Project | Previous Costs | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | Total By Phase
0
#3 Cascade Interchange | [16 empty] | 0
[6 empty] | 2021: Obligate in Nov. 2022 - Const in April 2024 | 0
| 3A - US 2 Interchange |  | 16364756 | 16628838 | 264082 | 0 | 0 | 0 | 0 | 741601 | 600216 | 7306266 | 5016969 | 2699704 | 0 |  | 16364756
[6 empty] | 2018: 0 | 0
|  | Preliminary Engineering | 1072179 | 1336261 | 264082 | 2022: 635658; 2023: 436521 | 1072179
|  | Environmental-Permitting | 269638 | 269638 |  | 2022: 105943; 2023: 163695 | 269638
|  | Right of Way | 0 | 0 | [12 empty] | 0
|  | Construction Engineering | 1421912 | 1421912 |  | 2024: 843031; 2025: 578881 | 1421912
|  | Construction | 12179115 | 12179115 |  | 2024: 5620204; 2025: 3859207; 2026: 2699704 | 12179115
|  | Contingency | 1421912 | 1421912 |  | 2024: 843031; 2025: 578881 | 1421912
0
0
| 3B - SR 28 and 35th Roundabout |  | 0 | 613296 | 0 | 139257 | 474039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 613296
0
|  | Preliminary Engineering | 0 | 502992 |  | 2018: 139257; 2019: 363735; 2020: 0 | 502992
|  | Environmental-Permitting | 0 | 0 |  | 2018: 0 | 0
|  | Right of Way | 0 | 110304 |  | 2018: 0; 2019: 110304; 2020: 0 | 110304
|  | Construction Engineering | 0 | 0 |  | 2018: 0; 2021: 0; 2022: 0 | 0
|  | Construction | 0 | 0 |  | 2018: 0; 2021: 0; 2022: 0 | 0
|  | Contingency | 0 | 0 |  | 2018: 0; 2021: 0; 2022: 0 | 0
0
0
0
Cost Grand Total |  |  | 16364756 | 17242134 | 264082 | 139257 | 474039 | 0 | 0 | 741601 | 600216 | 7306266 | 5016969 | 2699704 | 0 | 0 | 16978052
Net Surplus (Defecit) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note: Estimate Data provided by Douglas County
|  |  | Total Infra |  |  | 2018: 16364756
|  |  | Total Eligible Match - Future Costs (Non-Fed) |  |  | 2018: 0
|  |  | Total Eligible Match - Future Costs (Federal) |  |  | 2018: 0
Note on A43: Jeannie Beckett: FY21 Combined 3A and 3B into 1 project as WSDOT unfunded sub-project 3B and combined remaining funds into 3A
Note on E55: Steve King: Cost Estimate and Aging provided by WSDOT. Const. Eng. And Cont. est. by Sking
Note on H55: Jeannie Beckett: WSDOT combined decided that 3B was not be constructed and moved remainder of funds to 3A yr 2026

## 4 Sunset Highway
Sunset Highway
Legend
Project Totals
Eligible Future Costs and Sources
Pre-Match Invested
PE and ROW
|  | Construction | [6 empty] | <= Pre-Match | Match =>
Funding Sources
|  | Source | Eligible Future | Total Project | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | Total By Source 2018-2027
Local | [16 empty] | 0
|  | City of Wenatchee |  | 0 | [12 empty] | 0
|  | Douglas County |  | 0 | [12 empty] | 0
|  | Chelan - Douglas Transportation Council |  | 0 | [12 empty] | 0
|  | Link |  | 0 | [12 empty] | 0
|  | BNSF |  | 0 | [12 empty] | 0
|  | Other |  | 0
|  |  |  | 0 | [12 empty] | 0
| Local Subtotal |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
State | [16 empty] | 0
|  | Transit Grant |  | 0 | [12 empty] | 0
|  | FMSIB |  | 0 | [12 empty] | 0
|  | State of Washington - Requested |  | 0
|  | Connecting Washington Sunset Highway | 55857089 | 58522010 | 19794 | 3243 | 308122 | 2333762 | 6083766 | 9333764 | 6333764 | 7705795 | 11400000 | 10000000 | 5000000 | 0 | 58502216
|  | Connecting Washington North Wenatchee Avenue |  | 0
|  | CERB - Dept. of Commerce |  | 0
|  | Transportation Improvement Board |  | 0 | [12 empty] | 0
|  | Other |  | 7600000 | 2017: 7600000
0
| State Subtotal |  | 55857089 | 66122010 | 7619794 | 3243 | 308122 | 2333762 | 6083766 | 9333764 | 6333764 | 7705795 | 11400000 | 10000000 | 5000000 | 0 | 58502216
Federal | [16 empty] | 0
|  | STP |  | 0 | [12 empty] | 0
|  | INFRA |  | 0 | [12 empty] | 0
0
0
| Federal Subtotal |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
Funding Source Grant Total |  |  | 55857089 | 66122010 | 7619794 | 3243 | 308122 | 2333762 | 6083766 | 9333764 | 6333764 | 7705795 | 11400000 | 10000000 | 5000000 | 0 | 58502216
Project Costs
|  | Sub-project | Future Eligible | Total Project | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | Total By Phase
0 | bar: 2017
#4 Sunset Highway / SR28 Widening |  |  | 55857089 | 66122010 | 7619794 | 3243 | 308122 | 2333762 | 6083766 | 9333764 | 6333764 | 7705795 | 11400000 | 10000000 | 5000000 | 0 | 58502216
|  | Preliminary Engineering | 6357087 | 8722010 | 219794 | 3243 | 308122 | 1833764 | 1833764 | 1833764 | 1833764 | 855795 | 0 |  |  |  | 8502216
|  | Environmental-Permitting | 0 | 6000000 | 2017: 6000000 | 0
|  | Right of Way | 18500002 | 19000000 | 2020: 499998; 2021: 4250002; 2022: 7500000; 2023: 4500000; 2024: 1500000; 2025: 750000 | 19000000
|  | Construction Engineering | 4650000 | 4650000 | 2024: 802500; 2025: 1597500; 2026: 1500000; 2027: 750000 | 4650000
|  | Construction | 23250000 | 24650000 | 2017: 1400000; 2024: 4012500; 2025: 7987500; 2026: 7500000; 2027: 3750000 | 23250000
|  | Contingency | 3100000 | 3100000 | 2024: 535000; 2025: 1065000; 2026: 1000000; 2027: 500000 | 3100000
0
Cost Grand Total |  |  | 55857089 | 66122010 | 7619794 | 3243 | 308122 | 2333762 | 6083766 | 9333764 | 6333764 | 7705795 | 11400000 | 10000000 | 5000000 | 0 | 58502216
Net Surplus (Defecit) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Total INFRA |  | 0
[5 empty] | Total Match - Future Costs |  | 55857089
Total Match - Future Costs (Federal)
[6 empty] | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028
[5 empty] | PE |  | 3243 | 308122 | 1833764 | 1833764 | 1833764 | 1833764 | 855795 |  | 0 | 0
[5 empty] | RW |  |  |  | 499998 | 4250002 | 7500000 | 4500000 | 1500000 | 750000 | 0 | 0
[5 empty] | CN | 2024: 5350000; 2025: 10650000; 2026: 10000000; 2027: 5000000
Note on C43: Jeannie Beckett: No change in FY 21 Cashflow
Note on F45: Windows User: includes ninth and 28 roundabout design of $200k
Note on F46: Windows User: EIS
Note on F49: Windows User: Ninth and 28 Roundabout

## Match Calc - Baseline
Match Calculation Sheet - Baseline Option
Future Eligible Costs Only
| Includes City Match of | 12500000
#1 North Wenatchee Avenue and McKittrick
| Total INFRA Request | 21000000
| Total Non Fed Match | 31664893
| Total Fed Match | 0
#2 Confluence Parkway
| Total INFRA Request | 103049360
| Total Non Fed Match | 34900000
| Total Fed Match | 0
#3 Cascade Interchange
| Total INFRA Request | 16364756
| Total Non Fed Match | 0
| Total Fed Match | 0
#4 Sunset Highway
| Total INFRA Request | 0
| Total Non Fed Match | 55857089
| Total Fed Match | 0
Network Totals
| Total INFRA Request | 140414116
| Total Non Fed Match | 122421982
| Total Fed Match | 0
| Total of Match and INFRA | 262836098
| Total Match | 122421982
| Percentage Match | 46.58%